## Test Cases
# | This file is a template you can use to manually upload the test script as test case in SAP Cloud ALM. For more information, refer to SAP Note 3217691.
# | Any changes you make to the values of columns marked with [---] will be ignored.
# | 35E_S4CLD2608_BPD_EN_AE (2026-06-15 08:24:51)
Test Case GUID | Test Case Name* | [Scope GUID] | [Scope Name] | [Solution Process GUID] | [Solution Process Name] | [Solution Process Flow GUID] | [Solution Process Flow Name] | [Solution Process Flow Diagram GUID] | [Solution Process Flow Diagram Name] | [Test Case Priority] | [Test Case Owner] | Test Case Status | Activity GUID | Activity Title* | Activity Target Name | Activity Target URL | Action GUID | Action Title* | Action Instructions* | Action Expected Result
| Project Control – Research and Development Projects (35E) | [10 empty] | In Preparation |  | Additional Information |  |  |  | Information | <h1>Purpose</h1><h2>Overview</h2><p>This scenario describes a project where the research and development activities related to the design of a new product are managed. Therefore, it supports the product development process by managing the related project costs, milestones, budgets, and approvals. After releasing all or part of the project, the project is executed and project-related purchasing can be performed. Through the integration with SAP Intelligent Product Design, you can leverage advanced collaboration scenarios for project execution. Period-end closing activities such as overhead application or settlement can then be executed.</p>This document provides a detailed procedure for testing this scope item after solution activation, reflecting the predefined scope of the solution. Each process step, report, or item is covered in its own section, providing the system interactions (test steps) in a table view. Steps that are not in scope of the process but are needed for testing are marked accordingly. Project-specific steps must be added.<h1>Prerequisites</h1>This section summarizes all the prerequisites for conducting the test in terms of systems, users, master data, organizational data, other test data and business conditions.<h1>System Access</h1><table summary="" frame="border" border="1" rules="all"><colgroup><col width="50%"><col width="50%"></colgroup><thead><tr><th><p>System</p></th><th><p>Details</p></th></tr></thead><tbody><tr><td><p>System</p></td><td><p>Accessible via SAP Fiori launchpad. Your system administrator provides you with the URL to access the various apps assigned to your role.</p></td></tr></tbody></table><h1>Roles</h1>Create business roles using the following business role templates delivered by SAP and assign them to your individual test users.<div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="20%"><col width="20%"><col width="20%"><col width="20%"><col width="20%"></colgroup><thead><tr><th><p><span>Name (Role Template)</span></p></th><th><p><span>ID (Role Template)</span></p></th><th><p>Name (Launchpad Space)</p></th><th><p>ID (Launchpad Space)</p></th><th><p>Log On</p></th></tr></thead><tbody><tr><td><p><span>Project Financial Controller</span></p></td><td><p><span>SAP_BR_PROJ_FIN_CONTROLLER</span></p></td><td><p><span><span><span>Project Control - Finance</span></span></span></p></td><td><p><span><span><span>SAP_BR_PROJ_FIN_CONTROLLER</span></span></span></p></td><td></td></tr><tr><td><p><span>Configuration Expert - Business Process Configuration</span></p></td><td><p><span>SAP_BR_BPC_EXPERT</span></p></td><td><p><span><span><span>Business Process Configuration</span><span>/ </span><span>Business Process Configuration - Finance</span><span>/ </span><span>Business Process Configuration - Procurement</span><span>/ </span><span>Manage your Solution</span><span>/ </span><span>Business Process Configuration - Workflow</span><span>/ </span><span>Business Configuration - Feature Management</span><span>/ </span><span>Business Process Configuration - Extensibility Explorer</span><span>/ </span><span>Business Configuration - Transportation</span></span></span></p></td><td><p><span><span><span>SAP_BR_BPC_EXPERT</span><span>/ </span><span>SAP_FIN_SPT_BPC_EXPERT_PC</span><span>/ </span><span>SAP_MM_SPT_BIZ_PROC_CONFIGN_PC</span><span>/ </span><span>SAP_CA_SPT_IC_LND_BASE_PC</span><span>/ </span><span>SAP_CA_SPT_BPC_WORKFLOW_PC</span><span>/ </span><span>SAP_CA_SPT_BPC_FM_PC</span><span>/ </span><span>SAP_EI_SPT_BPC_EXT_PC</span><span>/ </span><span>SAP_TM_SPT_TRANSPCFG_PC</span></span></span></p></td><td></td></tr><tr><td><p><span>General Ledger Accountant</span></p></td><td><p><span>SAP_BR_GL_ACCOUNTANT</span></p></td><td><p><span><span><span>General Ledger</span></span></span></p></td><td><p><span><span><span>SAP_BR_GL_ACCOUNTANT</span></span></span></p></td><td></td></tr><tr><td><p><span>Cost Accountant - Overhead</span></p></td><td><p><span>SAP_BR_OVERHEAD_ACCOUNTANT</span></p></td><td><p><span><span><span>Overhead Accounting</span></span></span></p></td><td><p><span><span><span>SAP_BR_OVERHEAD_ACCOUNTANT</span></span></span></p></td><td></td></tr><tr><td><p><span>Analytics Specialist</span></p></td><td><p><span>SAP_BR_ANALYTICS_SPECIALIST</span></p></td><td><p><span><span><span>Analytics</span><span>/ </span><span>Analytics</span></span></span></p></td><td><p><span><span><span>SAP_CA_SPT_ANALYTICS_PC</span><span>/ </span><span>SAP_CORE_SPT_ANALYTICS_PC</span></span></span></p></td><td></td></tr><tr><td><p><span>Project Steering Committee Member</span></p></td><td><p><span>SAP_BR_PROJECT_STEER_MEMBER</span></p></td><td><p><span><span><span>Project Steering Committee</span></span></span></p></td><td><p><span><span><span>SAP_BR_PROJECT_STEER_MEMBER</span></span></span></p></td><td><p></p></td></tr><tr><td><p><span>Project Manager</span></p></td><td><p><span>SAP_BR_PROJECTMANAGER</span></p></td><td><p><span><span><span>Project Management</span></span></span></p></td><td><p><span><span><span>SAP_BR_PROJECTMANAGER</span></span></span></p></td><td><p></p></td></tr><tr><td><p><span>Business Process Specialist</span></p></td><td><p><span>SAP_BR_BUSINESS_PROCESS_SPEC</span></p></td><td><p><span><span><span>Business Process Management</span><span>/ </span><span>Business Process Management</span></span></span></p></td><td><p><span><span><span>SAP_BR_BUSINESS_PROCESS_SPEC</span><span>/ </span><span>SAP_CA_SPT_BPS_PC</span></span></span></p></td><td><p></p></td></tr></tbody></table></div><h1>Master Data, Organizational Data, and Other Data</h1><p>The organizational structure and master data of your company has been created in your system during activation. The organizational structure reflects the structure of your company. The master data represents materials, customers, and vendors, for example, depending on the operational focus of your company.</p><span aria-labelledby="n0t" style="color: #9f0000;"><div><strong>Caution</strong></div><p><span style="font-weight: bold;">Update Behavior of Predelivered Demo Data</span></p><p>In non-productive environments (such as starter systems, sandbox systems, or partner demo systems), SAP initially deploys demo data for your selected scope. You can use this data to test and evaluate business processes.</p><p>In a customer system, you can receive new or updated demo data after initial activation with further scope enhancements, provided the existing demo data wasn't changed in an incompatible way. If activation errors occur due to incompatible changes in demo data, you're responsible for resolving them. If you don't resolve the errors within a specific time frame, SAP reserves the right to deactivate demo data in your systems. In this case, you can continue by creating your own demo data. Alternatively, you can request that your systems be reprovisioned if you want to work with predelivered demo data again.</p><p>In partner systems, you can use the demo data deployed with the initial activation. No additional demo data will be deployed in the system with scope enhancements. You can only create additional demo data manually.</p></span><p>Use your own master data or the following sample data to go through the test procedure.</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="7.112375533428165%"><col width="16.35846372688478%"><col width="68.99004267425319%"><col width="7.539118065433855%"></colgroup><thead><tr><th><p>Data</p></th><th><p>Sample Value</p></th><th><p>Details</p></th><th><p>Comments</p></th></tr></thead><tbody><tr><td><p>Controlling Area </p></td><td><p><span style="font-family:Courier New;">A000</span></p></td><td><p><span style="font-family:Courier New;">Controlling Area A000</span></p></td><td></td></tr><tr><td><p>Company Code</p></td><td><p><span style="font-family:Courier New;">3310</span></p></td><td><p><span style="font-family:Courier New;">Company Code 3310</span></p></td><td></td></tr><tr><td><p>Plant</p></td><td><p><span style="font-family:Courier New;">3310</span></p></td><td><p><span style="font-family:Courier New;">Plant 1 AE</span></p></td><td></td></tr><tr><td><p>Cost Center</p></td><td><p><span style="font-family:Courier New;">33101501</span></p><p><span style="font-family:Courier New;">33101601</span></p><p></p><p><span style="font-family:Courier New;">33101321</span></p></td><td><p><span style="font-family:Courier New;">R&amp;D Cost center</span></p><p><span style="font-family:Courier New;">Marketing Cost Center</span></p><p><span style="font-family:Courier New;">Services/Consltg</span></p></td><td></td></tr><tr><td><p>Activity Types</p></td><td><p><span style="font-family:Courier New;">8</span></p><p><span style="font-family:Courier New;">11</span></p></td><td><p>Consulting</p><p>Personal Hours</p></td><td></td></tr><tr><td><p>Cost Rate</p></td><td><p>Actual and planned cost rates are maintained for the following combination of cost centers or activity types:</p><p>Cost centers: <span style="font-family:Courier New;">33101501</span>, <span style="font-family:Courier New;">33101101</span></p><p>Activity types: <span style="font-family:Courier New;">11</span></p></td><td></td><td><p>Cost Rates are defined time-dependent</p></td></tr><tr><td><p>G/L Account</p></td><td><p><span style="font-family:Courier New;">61007000</span></p></td><td><p>Trav. Expense – Airfare, Rail, Mileage</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">61003000</span></p></td><td><p>Travel Expenses – Hotel and Accommodation</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">61008000</span></p></td><td><p>Travel Expenses – Miscellaneous</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">10010000</span></p></td><td><p>Petty Cash</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">50309500</span></p></td><td><p>COGS - Licenses</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">65008300</span></p></td><td><p>Services – Genera</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">50305000</span></p></td><td><p>COGS Machine Time</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">51100000</span></p></td><td><p>Consumption – Raw Material</p></td><td></td></tr><tr><td>Continued</td><td><p><span style="font-family:Courier New;">50304000</span></p></td><td><p>Personnel Time</p></td><td></td></tr><tr><td><p>Profit Center</p></td><td><p><span style="font-family:Courier New;">YB600</span></p><p><span style="font-family:Courier New;">YB110</span></p></td><td><p>Shared Services</p><p>Product A</p></td><td></td></tr><tr><td><p>Functional Area</p></td><td><p><span style="font-family:Courier New;">YB75</span></p></td><td><p>Research &amp; Development</p></td><td><p></p></td></tr></tbody></table></div><p>You can find general information on how to create master data objects in the following Master Data Scripts (MDS):</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="50%"><col width="50%"></colgroup><thead><tr><th><p>MDS</p></th><th><p>Description</p></th></tr></thead><tbody><tr><td><p>BNM</p></td><td><p><span>Create Cost Center and Cost Center Group - MDS</span></p></td></tr><tr><td><p>BNN</p></td><td><p><span>Create Activity Type and Activity Type Hierarchy - MDS</span></p></td></tr><tr><td><p>BNG</p></td><td><p><span>Create G/L Account and Cost Element - MDS</span></p></td></tr><tr><td><p>3KW</p></td><td><p><span>Create CO Cost Rates - MDS</span></p></td></tr><tr><td><p>BNH</p></td><td><p><span>Create Profit Center - MDS</span></p></td></tr><tr><td><p>BHD</p></td><td><p><span>Create Purchasing Info Record - MDS</span></p></td></tr></tbody></table></div><h1>Business Conditions</h1><p>Before this scope item can be tested, the following business conditions must be met.</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="50%"><col width="50%"></colgroup><thead><tr><th><p>Scope Item ID</p></th><th><p>Business Condition</p></th></tr></thead><tbody><tr><td><p>1YF - <span>Project Review</span></p></td><td><p>To execute the project review and project collaboration functionalities, the project review <span>Project Review</span>(1YF) scope item must be activated.</p></td></tr><tr><td><p>4RF - <span>Project Control – Resourcing and Procurement</span></p></td><td><p>To execute demand planning for the project, the 4RF - <span>Project Control – Resourcing and Procurement</span>scope item must be activated</p></td></tr></tbody></table></div><h1>Preliminary Steps</h1><h1>Setting Up Custom Fields for Project (Optional)</h1><h2>Purpose</h2><p>In this step, you can maintain custom fields in the project header section.</p><h2>Procedure</h2><p>To execute this activity, carry out the relevant steps from the <cite>Key User Extensibility</cite>topic in the <cite>Extend and Integrate Your <span>SAP S/4HANA Cloud Public Edition</span></cite>guide to create and maintain custom fields that can be used to enhance applications.</p><p>The Business Context to be used is Project Header and Project Element.</p>
[14 empty] | Additional Information: Maintain Cost Rates |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you can maintain, check and update the actual cost rates.</p><h2>Procedure</h2>
[14 empty] | Additional Information: Maintain Cost Rates |  |  |  | Log on | <p>Log on to the Fiori Launchpad as a <span>Cost Accountant - Overhead</span></p>
[14 empty] | Additional Information: Maintain Cost Rates |  |  |  | Access the SAP Fiori App | <p>Open <span><span style="font-weight: bold;">Manage Cost Rates</span> - <span style="font-weight: bold;">Services</span> <span>(F3161)</span></span></p> | <p>The <span style="font-weight: bold;">Manage Cost Rates - Services </span> screen is displayed.</p>
[14 empty] | Additional Information: Maintain Cost Rates |  |  |  | Check Actual Cost Rates | <p>Make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Company Code</span>: <span style="font-family:Courier New;">3310</span></p><p><span style="font-weight: bold;">Valid On</span>: <span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Cost Center</span>: <span style="font-family:Courier New;">33101321</span> and <span style="font-family:Courier New;">33101101</span></p><p><span style="font-weight: bold;">Activity Type</span>: <span style="font-family:Courier New;">8</span></p><p><span style="font-weight: bold;">Currency</span>: <span style="font-family:Courier New;">AED</span></p><p>Check if there is a valid cost rate for given cost center, activity type, and period.</p> | <p>The actual cost rates for given cost centre, activity type and period are checked for valid values.</p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>You can skip the next step if there is a valid cost rate for given cost center, activity type, and period.</p></span>
[14 empty] | Additional Information: Maintain Cost Rates |  |  |  | Maintain Additional Actual Cost Rates | <p>Choose <span style="font-weight: bold;">Add</span> and make the following entries:</p><p><span style="font-weight: bold;">Company Code:</span><span style="font-family:Courier New;">3310</span></p><p><span style="font-weight: bold;">Cost Center</span>: <span style="font-family:Courier New;">33101321</span></p><p><span style="font-weight: bold;">Activity Type</span>: <span style="font-family:Courier New;">8</span></p><p><span style="font-weight: bold;">WBS Element</span>: <span style="font-family:Courier New;">&lt;this is an optional entry&gt;</span></p><p><span style="font-weight: bold;">From Fiscal Year</span>: <span style="font-family:Courier New;">Current Year</span></p><p><span style="font-weight: bold;">From Period</span>: <span style="font-family:Courier New;">Current Period</span></p><p><span style="font-weight: bold;"> Rate</span>: <span style="font-family:Courier New;">100</span></p><p><span style="font-weight: bold;">Currency</span>: <span style="font-family:Courier New;">AED</span></p><p><span style="font-weight: bold;">Per</span>:<span style="font-family:Courier New;">1</span></p><p><span style="font-weight: bold;">Activity Unit</span>: <span style="font-family:Courier New;">H</span></p><p>Choose <span style="font-weight: bold;">Save</span>.</p> | <p>The pop-up screen <span style="font-weight: bold;">Create Cost Rates-Company Code </span><span style="font-family:Courier New;">3310</span> appears.</p><p>Additional cost rates are created.</p>
[14 empty] | Additional Information: Maintain Cost Rates |  |  |  | Maintain Additional Actual Cost Rates | <p>Choose <span style="font-weight: bold;">Add</span> and make the following entries:</p><p><span style="font-weight: bold;">Company Code:</span><span style="font-family:Courier New;">3310</span></p><p><span style="font-weight: bold;">Cost Center</span>: <span style="font-family:Courier New;">33101101</span></p><p><span style="font-weight: bold;">Activity Type</span>: <span style="font-family:Courier New;">8</span></p><p><span style="font-weight: bold;">WBS Element</span>: <span style="font-family:Courier New;">&lt;this is an optional entry&gt;</span></p><p><span style="font-weight: bold;">From Fiscal Year</span>: <span style="font-family:Courier New;">Current Year</span></p><p><span style="font-weight: bold;">From Period</span>: <span style="font-family:Courier New;">Current Period</span></p><p><span style="font-weight: bold;">Rate</span>: <span style="font-family:Courier New;">100</span></p><p><span style="font-weight: bold;">Currency</span>: <span style="font-family:Courier New;">AED</span></p><p><span style="font-weight: bold;">Per</span>:<span style="font-family:Courier New;">1</span></p><p><span style="font-weight: bold;">Activity Unit</span>: <span style="font-family:Courier New;">H</span></p><p>Choose <span style="font-weight: bold;">Save</span>.</p> | <p>The pop-up screen <span style="font-weight: bold;">Create Cost Rates-Company Code </span><span style="font-family:Courier New;">3310</span> appears.</p><p>Additional cost rates are created.</p>
[14 empty] | Additional Information |  |  |  | Information | <h1>Maintain Financial Statement Versions</h1><h2>Procedure</h2><p>To execute this activity, run the preliminary step <cite>Maintain Financial Statement Versions</cite>from the <cite><span>Period-End Closing – Projects</span>(BNA)</cite>test script. </p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Information | <span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>If you are planning to use project coding mask for your projects, remember the following:</p><ul><li><p>You need to define the coding key before you create the project and determine exactly what your coding mask should be.</p></li><li><p>Coding mask cannot be created if project with same key already exists.</p></li><li><p>Coding mask once created can be deleted, if a project with the same key does not exist.</p></li></ul><p>With <span style="font-weight: bold;">Define Project Coding Mask</span>, you will be able to define the Coding Keys which determine the naming/nomenclature of the projects created in the scope items, namely, 1NT- <span>Project Control – Finance</span>, 35E- <span>Project Control – Research and Development Projects</span>and 35F- <span>Project Control – Capital Projects</span>. The usage of Project Coding Mask is not supported for the scope items such as J11- <span>Customer Project Management – Project-Based Services</span>and 1A8- <span>Internal Project Management – Project-Based Services</span>.</p></span><h2>Purpose</h2><p>The <span style="font-weight: bold;">Define Project Coding Mask</span>app is used to create the coding mask for the project structure. The coding mask applies to the external identification of project definitions as well as WBS elements. </p><h2>Procedure</h2><p>Depending on your configuration environment for <span>SAP S/4HANA Cloud Public Edition</span>, choose one of the following options:</p><p><span style="font-weight: bold;">Configure Your Solution</span>:</p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Log on | <p>Log on to the Fiori Launchpad as a </p><p><span>Configuration Expert - Business Process Configuration</span></p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Access the SAP Fiori App | <p>Open <span><span style="font-weight: bold;">Manage Your Solution</span> <span>(F1241)</span></span>.</p> | <p>The <span style="font-weight: bold;">Manage Your Solution</span> screen is displayed.</p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Navigate to Project Coding Mask SSCUI | <p>Choose the link <span style="font-weight: bold;">Configure Your Solution</span>.</p><p>Make the following entries:</p><p><span style="font-weight: bold;">Application Area</span>: <span style="font-family:Courier New;">Enterprise Portfolio &amp; Project Management</span></p><p><span style="font-weight: bold;">Sub Application Area</span>: <span style="font-family:Courier New;">Project Financials Control</span></p><p>Click on the line item displayed in the <span style="font-weight: bold;">Configuration Items</span> section </p><p>Select <span style="font-weight: bold;">Define Project Coding Mask</span> and choose <span style="font-weight: bold;">Configure</span></p> | <p>The <span style="font-weight: bold;">Change View "Project Number Editing'': Overview </span> screen is displayed.</p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Create a Coding Mask Entry | <p>Perform the following actions to create the coding mask:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><p>Enter the following details:</p><p><span style="font-weight: bold;">PrjID</span>: A</p><p><span style="font-weight: bold;">Coding mask</span>: /XXXXXX-00</p><p><span style="font-weight: bold;">Description</span>: Test Coding Mask for Key A</p><p><span style="font-weight: bold;">Lck</span>: &lt;Select/Deselect&gt;</p><p>Choose <span style="font-weight: bold;">Save</span>.</p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p>This step is optional.</p></li><li><p>Once the coding mask is created, deletion is not possible.</p></li><li><div>You cannot create commercial or internal projects in the project services processes, namely: <ul><li><p>Customer Project Management (J11) </p></li><li><p>Internal Project Management (1A8) </p></li></ul> that begins with any coding key defined for coding masks.</div></li></ul></span> | <p>Project Coding Mask will be saved. </p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Information | <p><span style="font-weight: bold;">SAP Central Business Configuration:</span></p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Log on | <p>Log on to the project experience in SAP Central Business Configuration.</p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Navigate to Project Coding Mask SSCUI | <p>Go to the <span style="font-weight: bold;">Business Processes Configuration</span> app. To locate the activity in the tree view, search for the following activity: <span style="font-weight: bold;">Define Project Coding Mask</span>.</p><p>Choose <span style="font-weight: bold;">Open Documentation</span> for the found line item to see more details about this configuration activity.</p><p>Choose the link to navigate directly to the <span>SAP S/4HANA Cloud Public Edition</span> system. Log on to the SAP Fiori launchpad as a <span>Configuration Expert - Business Process Configuration</span>.</p> | <p>The <span style="font-weight: bold;">Change View "Project Number Editing": Overview </span> screen is displayed.</p>
[14 empty] | Additional Information: Create Project Coding Mask |  |  |  | Create a Coding Mask Entry | <p>Perform the following actions to create the coding mask:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><p>Enter the following details:</p><p><span style="font-weight: bold;">PrjID</span>: A</p><p><span style="font-weight: bold;">Coding mask</span>: /XXXXXX-00</p><p><span style="font-weight: bold;">Description</span>: Test Coding Mask for Key A</p><p><span style="font-weight: bold;">Lck</span>: &lt;Select/Deselect&gt;</p><p>Choose <span style="font-weight: bold;">Save</span>.</p><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p>This step is optional.</p></li><li><p>Once the coding mask is created, deletion is not possible.</p></li><li><div>You cannot create commercial or internal projects in the project services processes, namely: <ul><li><p>Customer Project Management (J11) </p></li><li><p>Internal Project Management (1A8) </p></li></ul> that begins with any coding key defined for coding masks.</div></li></ul></span> | <p>Project Coding Mask will be saved. </p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Information | <span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>This is an optional step. Before creating a Project Type, you must consider the following guidelines.</p><p>The Project Type key is unique. Determine exactly what your Project Type key should be as you cannot edit/delete project type key once created.</p><p>Project Type does not influence program control or screen selection, instead, it is used as a filtering criteria for projects.</p></span><h2>Purpose</h2><p>Project Type is generally used to group or classify projects, it is primarily used for the reporting. The <span style="font-weight: bold;">Create Project Types for WBS Elements</span>app is used to create the project type.</p><h2>Procedure</h2><p>Depending on your configuration environment for <span>SAP S/4HANA Cloud Public Edition</span>, choose one of the following options:</p><p><span style="font-weight: bold;">Configure Your Solution</span>:</p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Log on | <p>Log on to the Fiori Launchpad as a <span>Configuration Expert - Business Process Configuration</span>.</p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Manage Your Solution</span> <span>(F1241)</span></span>.</p> | <p>The <span style="font-weight: bold;">Manage Your Solution </span> screen is displayed.</p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Navigate to Create Project Types for WBS Elements SSCUI | <p>Choose the link <span style="font-weight: bold;">Configure your solution</span>.</p><p>Make the following entries</p><p><span style="font-weight: bold;">Application Area</span>: <span style="font-family:Courier New;">Enterprise Portfolio &amp; Project Management</span></p><p><span style="font-weight: bold;">Sub Application Area</span>: <span style="font-family:Courier New;">Project Financials Control</span></p><p>Click on the line item displayed in the worklist section </p><p>Select <span style="font-weight: bold;">Create Project Types for WBS Elements</span> and choose <span style="font-weight: bold;">Configure</span></p> | <p>The <span style="font-weight: bold;">Create Project Types for WBS Elements </span>app is displayed.</p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Create a Project Type | <p>Perform the following actions to create the project type:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><p>Enter the details as mentioned in the following example :</p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Typ</span>: <span style="font-family:Courier New;">RD</span></p><p><span style="font-weight: bold;">Description</span>: <span style="font-family:Courier New;">RD Projects</span></p></span><p>Choose <span style="font-weight: bold;">Save</span>.</p> | <p>Project Type is saved.</p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Information | <p><span style="font-weight: bold;">SAP Central Business Configuration:</span></p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Log on | <p>Log on to the project experience in SAP Central Business Configuration. </p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Open Create Project Types for WBS Elements SSCUI | <p>Go to the <span style="font-weight: bold;">Business Processes Configuration</span> app. To locate the activity in the tree view, search for the following activity: <span style="font-weight: bold;">Create Project Types for WBS Elements</span>.</p><p>Choose <span style="font-weight: bold;">Open Documentation</span> for the found line item to see more details about this configuration activity.</p><p>Choose the link to navigate directly to the <span>SAP S/4HANA Cloud Public Edition</span> system. Log on to the SAP Fiori launchpad as a <span>Configuration Expert - Business Process Configuration</span>.</p>
[14 empty] | Additional Information: Create Project Types for WBS Elements (Optional) |  |  |  | Create a Project Type | <p>Perform the following actions to create the project type:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><p>Enter the details as mentioned in the following example :</p><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Typ</span>: <span style="font-family:Courier New;">RD</span></p><p><span style="font-weight: bold;">Description</span>: <span style="font-family:Courier New;">RD Projects</span></p></span><p>Choose <span style="font-weight: bold;">Save</span>.</p> | <p>Project Type is saved.</p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Information | <span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>This is an optional step. Before creating a Budget Availability Profile, you must consider the following guidelines.</p><p>There are various restrictions when you try to change the budget availability control settings. If commitments or actual costs are already posted, you can no longer activate the checks.</p></span><h2>Purpose</h2><p>The <span style="font-weight: bold;">Maintain Budget Availability Profile</span>app is used to create the Budget Availability control profile.</p><h2>Prerequisites</h2><p>If you intend to use Project Budget, make sure that you activate the non-standard scope item <span>Predictive Commitments Management</span>(2I3) which is a prerequisite for budgeting. Once activated, commitment management ledger 0E is active and applicable for all company codes and countries/regions. These commitments are updated in Extension Ledger 0E (predelivered) in ACDOCA table. Commitments are reduced by various business transactions such as goods receipt. The default content for Project Budgeting utilizes profiles PS001 and you can either update this profile or create your own profile via SSCUI <span style="font-weight: bold;">Maintain Budget Availability Control Profile for Projects</span>. </p><p>Ensure that you perform the <span style="font-weight: bold;">Preliminary Steps</span>of this document to update the following: </p><ul><li><p>Maintain Financial statement YPS2 </p></li><li><p>Tag ACT_COST which is mandatory for G/Ls relevant for Budget check. Note that currently Commitment/Budget do not work for Purchase order without material. </p></li><li><p>Maintain Financial Statement Visions (FSV)</p></li><li><p>Assign Semantic Tags for FSV </p></li><li><p>Set Report Relevancy </p></li><li><p>Replicate Runtime Hierarchy. Make sure G/Ls relevant for Budget are part of this structure. </p></li></ul>To view commitments in the report, an open purchase order and/or requisition must exist. For details on creating purchase orders, refer to <span>Consumable Purchasing</span> (BNX). <h2>Procedure</h2><p>Depending on your configuration environment for <span>SAP S/4HANA Cloud Public Edition</span>, choose one of the following options:</p><p><span style="font-weight: bold;">Configure Your Solution</span>:</p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Log on | <p>Log on to the Fiori Launchpad as a <span>Configuration Expert - Business Process Configuration</span>.</p> | <p></p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Access the SAP Fiori App | <p>Open <span><span style="font-weight: bold;">Manage Your Solution</span> <span>(F1241)</span></span>.</p> | <p>The <span style="font-weight: bold;">Manage Your Solution</span> screen is displayed.</p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Navigate to Maintain Budget Availability Control Profile for Projects | <p>Choose the link <span style="font-weight: bold;">Configure your solution</span>.</p><p>Make the following entries:</p><p><span style="font-weight: bold;">Application Area:</span><span style="font-family:Courier New;">Finance</span></p><p><span style="font-weight: bold;">Sub Application Area:</span><span style="font-family:Courier New;">Overhead Cost Management</span></p><p>Click on the line item with Item Name <span style="font-weight: bold;">Budget Management </span>from the worklist section.</p><p>Select <span style="font-weight: bold;">Maintain Budget Availability Control Profile for Projects </span> and choose <span style="font-weight: bold;">Configure</span></p> | <p>The <span style="font-weight: bold;">Maintain Budget Availability Profile</span> app is displayed.</p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Create an Availability Control Profile Entry | <p>Perform the following actions to create the availability control profile:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><p>Enter the details similar to the following example:</p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Profile</span>: <span style="font-family:Courier New;">ZS001</span></p><p><span style="font-weight: bold;">Availy Ctrl Type</span>: <span style="font-family:Courier New;">Project System</span></p><p><span style="font-weight: bold;">Budget Availy Ctrl: Profile Name </span>: <span style="font-family:Courier New;">Default Bdgt Availability prfl</span></p><p><span style="font-weight: bold;">Time Range</span>: <span style="font-family:Courier New;">Annual Budget / Overall Budget</span></p><p><span style="font-weight: bold;">Budget Currency</span>: <span style="font-family:Courier New;">Global Currency/Project Currency</span></p></span><p>Press <span style="font-family:Courier New;">Enter</span>.</p><div><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p><span style="font-weight: bold;">Overall Budget</span> needs to be selected if you want to perform the budget check across Fiscal years whereas <span style="font-weight: bold;">Annual Budget</span> needs to be selected if you want to perform the check per Fiscal year.</p></li><li><p><span style="font-weight: bold;">Gobal Currency</span> needs to be selected if you want to calculate the financials at controlling area level whereas <span style="font-weight: bold;">Project Currency</span> needs to be selected if you want to check financials at project level.</p></li></ul></span></div><p>For this newly created Availability Control Profile, maintain the Semantic Tags and Tolerance Limits.</p><p>Select the AVC profile and choose <span style="font-weight: bold;">Semantic Tags </span>and maintain entries as shown in the following example:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><span aria-labelledby="n3t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Sem. Tag</span>: <span style="font-family:Courier New;">ACT_COST</span></p><p><span style="font-weight: bold;">Semantic Tag Name</span>: <span style="font-family:Courier New;">Actual Cost</span></p><p><span style="font-weight: bold;">% of Budget used Before First Notification</span>: <span style="font-family:Courier New;">80%</span></p><p><span style="font-weight: bold;">% Increment for Further Notifications</span>: <span style="font-family:Courier New;">5%</span></p></span><p>Press <span style="font-family:Courier New;">Enter</span>.</p><p>Select the Semantic tag and choose <span style="font-weight: bold;">Tolerance Limits</span> and maintain entries as shown in the following example:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><span aria-labelledby="n4t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Acty Grp</span>: <span style="font-family:Courier New;">All Activity Groups</span></p><p><span style="font-weight: bold;">MsgType</span>: <span style="font-family:Courier New;">Warning/Error</span></p><p><span style="font-weight: bold;">%</span>: <span style="font-family:Courier New;">90.00</span></p></span><p>Press <span style="font-family:Courier New;">Enter</span>.</p><p>Choose <span style="font-weight: bold;">Save</span>.</p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Information | <p><span style="font-weight: bold;">SAP Central Business Configuration:</span></p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Log on | <p>Log on to the project experience in SAP Central Business Configuration.</p> | <p></p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Navigate to Maintain Budget Availability Profile SSCUI | <p>Go to the <span style="font-weight: bold;">Business Processes Configuration</span> app. To locate the activity in the tree view, search for the following activity: <span style="font-weight: bold;">Maintain Budget Availability Profile using Self Service</span>.</p><p>Choose <span style="font-weight: bold;">Open Documentation</span> for the found line item to see more details about this configuration activity.</p><p>Choose the link to navigate directly to the <span>SAP S/4HANA Cloud Public Edition</span> system. Log on to the SAP Fiori launchpad as a <span>Configuration Expert - Business Process Configuration</span>.</p> | <p>The <span style="font-weight: bold;">Maintain Budget Availability Profile</span> screen is displayed.</p>
[14 empty] | Additional Information: Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional) |  |  |  | Create an Availability Control Profile Entry | <p>Perform the following actions to create the availability control profile:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><p>Enter the details similar to the following example:</p><span aria-labelledby="n5t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Profile</span>: <span style="font-family:Courier New;">ZS001</span></p><p><span style="font-weight: bold;">Availy Ctrl Type</span>: <span style="font-family:Courier New;">Project System</span></p><p><span style="font-weight: bold;">Budget Availy Ctrl: Profile Name </span>: <span style="font-family:Courier New;">Default Bdgt Availability prfl</span></p><p><span style="font-weight: bold;">Time Range</span>: <span style="font-family:Courier New;">Annual Budget / Overall Budget</span></p><p><span style="font-weight: bold;">Budget Currency</span>: <span style="font-family:Courier New;">Global Currency/Project Currency</span></p></span><p>Press <span style="font-family:Courier New;">Enter</span>.</p><div><span aria-labelledby="n6t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p><span style="font-weight: bold;">Overall Budget</span> needs to be selected if you want to perform the budget check across Fiscal years whereas <span style="font-weight: bold;">Annual Budget</span> needs to be selected if you want to perform the check per Fiscal year.</p></li><li><p><span style="font-weight: bold;">Gobal Currency</span> needs to be selected if you want to calculate the financials at controlling area level whereas <span style="font-weight: bold;">Project Currency</span> needs to be selected if you want to check financials at project level.</p></li></ul></span></div><p>For this newly created Availability Control Profile, maintain the Semantic Tags and Tolerance Limits.</p><p>Select the AVC profile and choose <span style="font-weight: bold;">Semantic Tags </span>and maintain entries as shown in the following example:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><span aria-labelledby="n7t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Sem. Tag</span>: <span style="font-family:Courier New;">ACT_COST</span></p><p><span style="font-weight: bold;">Semantic Tag Name</span>: <span style="font-family:Courier New;">Actual Cost</span></p><p><span style="font-weight: bold;">% of Budget used Before First Notification</span>: <span style="font-family:Courier New;">80%</span></p><p><span style="font-weight: bold;">% Increment for Further Notifications</span>: <span style="font-family:Courier New;">5%</span></p></span><p>Press <span style="font-family:Courier New;">Enter</span>.</p><p>Select the Semantic tag and choose <span style="font-weight: bold;">Tolerance Limits</span> and maintain entries as shown in the following example:</p><p>Choose <span style="font-weight: bold;">New Entries</span></p><span aria-labelledby="n8t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">Acty Grp</span>: <span style="font-family:Courier New;">All Activity Groups</span></p><p><span style="font-weight: bold;">MsgType</span>: <span style="font-family:Courier New;">Warning/Error</span></p><p><span style="font-weight: bold;">%</span>: <span style="font-family:Courier New;">90.00</span></p></span><p>Press <span style="font-family:Courier New;"></span>.</p><p>Choose <span style="font-weight: bold;">Save</span>.</p>
[14 empty] | Additional Information: Manage Situation Types (Optional) |  |  |  | Information | <h2>Purpose</h2><div>To monitor budget threshold for the project, you need to configure the situation type. In this procedure, you configure the situation type by using template.<span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>For details on situations and the process to set up situation types, see the <cite>Setting Up <span>Situation Handling</span>(31N)</cite>guide.</p></span></div><h2>Procedure</h2>
[14 empty] | Additional Information: Manage Situation Types (Optional) |  |  |  | Log on | <p>Log on to the SAP Fiori launchpad as a <span>Business Process Specialist</span></p>
[14 empty] | Additional Information: Manage Situation Types (Optional) |  |  |  | Open Manage Situation Types | <p>Open <span><span style="font-weight: bold;">Manage Situation Types</span> <span>(F2947)</span></span> app.</p> | <p>The <span style="font-weight: bold;">Manage Situation Types</span> screen is displayed.</p>
[14 empty] | Additional Information: Manage Situation Types (Optional) |  |  |  | Select the Template to Copy | <p>In the <span style="font-weight: bold;">Situation Templates</span> section, enter the ID <span style="font-family:Courier New;">EPPM_PROJBUDGETTHRESHOLDEXCEEDED</span> and choose <span style="font-weight: bold;">Go</span>.</p><p>Select <span style="font-weight: bold;">EPPM_PROJBUDGETTHRESHOLDEXCEEDED</span>, then choose <span style="font-weight: bold;">Copy</span>.</p> | <p>The <span style="font-weight: bold;">Situation Type</span> screen is displayed.</p>
[14 empty] | Additional Information: Manage Situation Types (Optional) |  |  |  | Maintain the Situation | <p>Make the following entries and choose <span style="font-weight: bold;">Save</span>:</p><p><span style="font-weight: bold;">Admin Information</span></p><p><span style="font-weight: bold;">ID</span>: &lt;ID Name&gt;</p><p><span style="font-weight: bold;">Name</span>: &lt;ID Description&gt;</p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-weight: bold;">ID</span>: <span style="font-family:Courier New;">Z_BUDGET THRESHOLD</span></p><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">Budget Consumption Situation</span></p></span><p><span style="font-weight: bold;">Situation Display</span></p><p><span style="font-weight: bold;">Short Description</span>:</p><p><span style="font-weight: bold;">Details</span>:</p><p><span style="font-weight: bold;">Notification</span>:</p><p><span style="font-weight: bold;">Resend Notifications</span>: <span style="font-family:Courier New;">YES</span></p><p><span style="font-weight: bold;">Conditions</span></p><p>Maintain the values against the corresponding attributes/ filters to configure the conditions and use this function.</p><p><span style="font-weight: bold;">Recipients</span></p><p><span style="font-weight: bold;">Responsibility by teams</span>: Choose <span style="font-weight: bold;">Create</span> and maintain the team created through the 'Manage Teams and Responsibilities' app and maintain the value <span style="font-family:Courier New;">Project Financial Controller</span> in the field <span style="font-weight: bold;">Member Functions</span> if you intend to send notifications triggered by the situation Management to the Project Financial Controller, who is part of central project management team responsible for multiple projects.</p><p><span style="font-weight: bold;">Responsibility Rules</span>: Choose and select "Get the Project Responsible users (Project Financial Controller and Project Manager)" shown in the Rule list if you intend to trigger notifications to the project specific team defined in the project brief application.</p> | <p>The situation type is maintained</p>
[14 empty] | Additional Information: Manage Situation Types (Optional) |  |  |  | Enable The Situation Type | <p>Choose <span style="font-weight: bold;">Enable</span>, it will change from <span style="font-weight: bold;">NO</span> to <span style="font-weight: bold;">YES</span>.</p> | <p></p>
[14 empty] | Additional Information: Manage Teams and Responsibilities for Projects (Optional) |  |  |  | Information | <h2>Purpose</h2><div>In this procedure, you define teams which are responsible for handling multiple projects across organisations.<span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>For details on the process of setting up teams and responsibility determination, see the <cite>Setting Up <span>Responsibility Management</span>(1NJ)</cite>guide.</p></span></div><div>You can also define your own responsibility management (functions, teams, and responsibilities) by making use of the following SSCUIs:<ul><li><p>Map Function Profiles to Standard Team Category</p></li><li><p>Classify Functions for Standard Team Category</p></li><li><p>Map Custom Responsibility Definitions to Standard Team Category</p></li><li><p>Define Team Types </p></li></ul></div><h2>Procedure</h2>
[14 empty] | Additional Information: Manage Teams and Responsibilities for Projects (Optional) |  |  |  | Log on | <p>Log on on to the SAP Fiori launchpad as a <span>Business Process Specialist</span>. </p>
[14 empty] | Additional Information: Manage Teams and Responsibilities for Projects (Optional) |  |  |  | Access the App | <p>Open <span><span style="font-weight: bold;">Manage Teams and Responsibilities</span> <span>(F2412)</span></span> .</p><p>Choose <span style="font-weight: bold;">Create</span>.</p> | <p>The <span style="font-weight: bold;">Team</span> screen is displyed.</p>
[14 empty] | Additional Information: Manage Teams and Responsibilities for Projects (Optional) |  |  |  | Maintain the Team details | <p>Make the following entries and choose <span style="font-weight: bold;">Save</span>:</p><p>In the <span style="font-weight: bold;">General Information</span> tab:</p><ul><li><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">Team_EPPM</span></p></li><li><p><span style="font-weight: bold;">Description:</span><span style="font-family:Courier New;">Team of EPPM</span></p></li><li><p><span style="font-weight: bold;">Status</span>:<span><span style="font-family:Courier New;">Enabled</span></span></p></li><li><p><span style="font-weight: bold;">Type</span>:<span style="font-family:Courier New;">SEPPM_PFC</span></p></li></ul><p>In the <span style="font-weight: bold;">Team Members</span> tab:</p><p>Choose <span style="font-weight: bold;"> + Add</span>, and maintain the following values:</p><ul><li><p><span style="font-weight: bold;">Business Partner</span>: use the search function to find the business partner of <span>Project Financial Controller</span></p></li><li><p><span style="font-weight: bold;">Functions</span>: <span>Project Financial Controller</span></p></li></ul> | <p></p>
[14 empty] | Additional Information: Manage Teams and Responsibilities for Projects (Optional) |  |  |  | Create the team | <p>Choose <span style="font-weight: bold;">Create</span>.</p> | <p>The team is created</p>
[14 empty] | Test Procedures |  |  |  | Information | This section describes test procedures for each process step that belongs to this scope item.
[14 empty] | Create R&amp;D Project |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you can create an R&amp;D project with project definition using the <span style="font-weight: bold;">Project Control</span>fiori app. </p><p>For hierarchical project accounting requirements, you can also create a hierarchical project structure by calling up the Project Planning application from the <span style="font-weight: bold;">Project Control</span>app.</p><h2>Procedure</h2>
[14 empty] | Create R&amp;D Project |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Create R&amp;D Project |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Project Control - Enterprise Projects</span> <span>(F3215)</span></span> .</p> | <p>The <span style="font-weight: bold;">Project Control - List</span> screen is displayed.</p>
[14 empty] | Create R&amp;D Project |  |  |  | Create Project: Definition | <p>Choose <span style="font-weight: bold;">Create</span>.</p><p>Make the following entries in the <span style="font-weight: bold;">Header</span> tab:</p><p><span style="font-weight: bold;">Project Name</span>: <span style="font-family:Courier New;">e-Bike</span></p><p><span style="font-weight: bold;">Project ID</span>: <span style="font-family:Courier New;">RnD_000XX (For Example: RnD_00001)</span></p><p><span style="font-weight: bold;">Project Profile</span>: <span style="font-family:Courier New;">Overhead Project</span></p><p><span style="font-weight: bold;">Planned Start: </span><span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Planned Finish</span><span style="font-family:Courier New;">: Today + 3 months</span></p><p>Make the following entries in the <span style="font-weight: bold;">General Information</span> tab: </p><p><span style="font-weight: bold;">Responsible Cost Centre</span>: <span style="font-family:Courier New;">33101501</span>(R&amp;D Cost Center)</p><p><span style="font-weight: bold;">Profit Center</span>: <span style="font-family:Courier New;">YB110 (Product A)</span></p><p><span style="font-weight: bold;">Project Currency</span>: <span style="font-family:Courier New;">AED</span> (Automatically filled based on the cost center)</p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>You can specify the currency at project level different from controlling area currency, to run project specific financial reports.</p></span><p><span style="font-weight: bold;">Project Manager</span>:<span style="font-family:Courier New;">the Project Manager ID</span></p><p>In the <span style="font-weight: bold;">Attachments</span> tab, do the following:</p><p>Choose <span style="font-weight: bold;">Upload</span> to upload project relevant documents from your local drive.</p><p>Choose <span style="font-weight: bold;">Create</span>.</p><p>A message tells you that the object is saved.</p><p>When the project definition is created, Project Summary Task WBS Element will be created.</p> | <p>Project is created with the provided definition parameters.</p><p>One WBS Element with the following details is created under the project :</p><p>WBS Element ID:<span style="font-family:Courier New;"> RnD_000XX</span></p><p>Project Name: <span style="font-family:Courier New;">Overhead Project</span></p>
[14 empty] | Create R&amp;D Project |  |  |  | Add Values to the Project Summary Task WBS Element. | <p>Once the project is created (<span style="font-family:Courier New;">RnD_000XX</span>), choose <span style="font-weight: bold;">Edit </span>from the header section<span style="font-weight: bold;">.</span></p><p>Make the following entries in the <span style="font-weight: bold;">General Information</span> tab:</p><p><span style="font-weight: bold;">Plant:</span><span style="font-family:Courier New;">3310</span></p><p><span style="font-weight: bold;">Functional Area </span>:<span style="font-family:Courier New;">YB75 (Other expenses)</span></p><p>Make the following entries in the <span style="font-weight: bold;">Control</span> tab:</p><p><span style="font-weight: bold;">Costing Sheet:</span><span style="font-family:Courier New;">3310PI</span></p><p>The following are optional entries, maintain them according to your requirements.</p><div><span style="font-weight: bold;">Budget Availability Control Profile</span>: Select the Budget Availability Profile created using SSCUI as mentioned in Preliminary Step (Maintain Budget Availability Profile using Self Service Configuration (SSC) UI app (Optional)) <span aria-labelledby="n1t" style="color: #346187; "><div><strong>Example</strong></div><p><span style="font-family:Courier New;">ZS001</span></p></span></div><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Note</strong></div><p>If project currency is maintained, you can assign a budget availability control profile where the budget currency is maintained as <span style="font-weight: bold;">Global Currency</span> or <span style="font-weight: bold;">Project Currency</span></p><p>If project currency is not maintained, you can only assign a budget availability control profile where the budget currency is maintained as <span style="font-weight: bold;">Global Currency</span>.</p></span><p><span style="font-weight: bold;">Budget Availability Control Profile is active</span>: <span style="font-family:Courier New;">Checked</span></p><div><span aria-labelledby="n3t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p>You can define your own budget availability profile using an SSCUI.</p></li><li><p>As soon as you have planned budget for your project and activated the budget availability control, the hierarchy changes are no longer possible.</p></li></ul></span></div><span aria-labelledby="n4t" style="color: #346187; "><div><strong>Note</strong></div><p>You will be able to see Joint Venture (JV) attributes under the section<span style="font-weight: bold;"> Joint Venture Accounting</span> during project creation, if the Joint Venture accounting functionality has been activated in the system. For the detailed explanation on JV attributes, you can refer to the scope item 3F7-<span>Joint Venture Accounting</span> . </p></span><p><span style="font-weight: bold;">Block Functions</span></p><p><span style="font-weight: bold;">Time Recording</span>: <span style="font-family:Courier New;">&lt;Selected/Not Selected&gt;</span></p><p><span style="font-weight: bold;">Activity Allocation</span>: <span style="font-family:Courier New;">&lt;Selected/Not Selected&gt;</span></p><p><span style="font-weight: bold;">Purchasing</span>: <span style="font-family:Courier New;">&lt;Selected/Not Selected&gt;</span></p><p><span style="font-weight: bold;">Concur Expense Posting</span>: <span style="font-family:Courier New;">&lt;Selected/Not Selected&gt;</span></p><div><span style="font-weight: bold;">Other Expense Posting</span>: <span style="font-family:Courier New;">&lt;Selected/Not Selected&gt;</span><span aria-labelledby="n5t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p>You can also block certain functions based on the business requirement for the project being created.</p></li><li><p>The Block functions need to be set at the individual WBS Element level to enable the functionality.</p></li><li><p>Setting up the block functions at Project Header level will not impact the complete project hierarchy.</p></li></ul></span></div><p>Choose <span style="font-weight: bold;">Save</span></p><p>A message tells you that the project is saved.</p> | <p>WBS Element is updated with all the provided parameters. </p><div><span aria-labelledby="n6t" style="color: #346187; "><div><strong>Note</strong></div><p>In case you have entered a budget availability control profile and activated the budget availability control, all postings resulting into commitments or actual costs will be checked against the available budget of the WBS element used as account assignment object.</p><p>In case the WBS element itself does not have any budget, the next higher level budget carrying WBS element will be used for the budget availability check.</p><p>Depending on the tolerance limits defined for the availability control profile, the system can raise warning or error messages.</p><p>Depending on the Time Range defined for the availability control profile, you will be able to check the budget consumption for a particular fiscal year or across fiscal years.</p><p>This setting is valid for all kind of expense postings and expected expense postings (for example, purchase requisition or purchase orders) to a WBS element.</p><p>Warning messages from budget availability check are not shown in case of automatic periodic postings and certain goods movement.</p></span></div>
[14 empty] | Create R&amp;D Project |  |  |  | Navigate to Project Planning | <p>Once the project is created (<span style="font-family:Courier New;">RnD_000XX</span>), choose <span style="font-weight: bold;">Related Apps </span>from the header section<span style="font-weight: bold;">. </span>A pop-up screen appears</p><p>From the pop-up screen, select <span style="font-weight: bold;">Project Planning</span> to go to the <span style="font-weight: bold;">Project Planning</span> app.</p><div><span aria-labelledby="n7t" style="color: #346187; "><div><strong>Note</strong></div><p>By default, the project will be in displayed mode, to edit the project, choose <span style="font-weight: bold;">Edit</span></p></span></div> | <p>You will navigate to <span style="font-weight: bold;">Project Planning</span> app and will be able to make further entries.</p>
[14 empty] | Create R&amp;D Project |  |  |  | Create WBS Elements under Project Summary Task WBS Element. | <p>In the Project Structure view, select WBS Element (<span style="font-weight: bold;">RnD_000XX</span>) created in the above step, and choose <span style="font-weight: bold;">Create </span>.</p><p><span style="font-weight: bold;">ID</span>: <span style="font-family:Courier New;">RnD_000XX_01</span></p><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">WBS for Concept Phase</span></p><p><span style="font-weight: bold;">Profit Center</span>: <span style="font-family:Courier New;">&lt;This data is pre-populated from the first WBS level&gt;</span></p><p><span style="font-weight: bold;">Resp. Cost Cntr:</span><span style="font-family:Courier New;">33101501</span> (This data is pre-populated from first WBS level) </p><p><span style="font-weight: bold;">Planned Start:</span><span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Planned Finish:</span><span style="font-family:Courier New;">Today + 3 months</span></p><p>In the Project Structure view, select WBS Element (RnD_000XX) created in the above step, and choose <span style="font-weight: bold;">Create</span></p><p><span style="font-weight: bold;">ID</span>: <span style="font-family:Courier New;">RnD_000XX_02</span></p><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">WBS for Design Phase</span></p><p><span style="font-weight: bold;">Profit Center</span>: <span style="font-family:Courier New;">&lt;This data is pre-populated from the first WBS level&gt;</span></p><p><span style="font-weight: bold;">Resp. Cost Cntr:</span><span style="font-family:Courier New;">33101501</span> (This data is pre-populated from first WBS level) </p><p><span style="font-weight: bold;">Planned Start:</span><span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Planned Finish:</span><span style="font-family:Courier New;">Today + 3 months</span></p><p>In the Project Structure view, select WBS Element (RnD_000XX) created in the above step, and choose Create Work Package.</p><p><span style="font-weight: bold;">ID</span>: <span style="font-family:Courier New;">RnD_000XX_03</span></p><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">WBS for Prototype Phase</span></p><p><span style="font-weight: bold;">Profit Center</span>: <span style="font-family:Courier New;">&lt;This data is pre-populated from the first WBS level&gt;</span></p><p><span style="font-weight: bold;">Resp. Cost Cntr:</span><span style="font-family:Courier New;">33101501</span> (This data is pre-populated from first WBS level) </p><p><span style="font-weight: bold;">Planned Start:</span><span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Planned Finish:</span><span style="font-family:Courier New;">Today + 3 months</span></p><div><span aria-labelledby="n8t" style="color: #346187; "><div><strong>Note</strong></div><p>Create WBS Element structure based on your requirements</p></span></div><p>You can also create WBS Element by making use of the <span style="font-weight: bold;">Copy </span> functionality available in the Project Planing Application.</p><p>You can also include WBS Element of another project by making use of the <span style="font-weight: bold;">Include</span> functionality available in the project planning application (While Including the WBS Elements, the existing demands and settlement rules of the source WBS Element are not included).</p> | <p>Project with WBS Element structure is updated with the provided parameters.</p>
[14 empty] | Create R&amp;D Project |  |  |  | Save Project Structure | <p>Choose <span style="font-weight: bold;">Save</span>.</p> | <p>Project with WBS Element structure is saved</p>
[14 empty] | Describe Project (Optional) |  |  |  | Information | <h2>Purpose</h2><p>In this activity, the <span>Project Manager</span>describes the project details such as Milestones, Status and adds the Project team for the first time.</p><h2>Procedure</h2><p>To execute this activity, perform the steps ‘Describe Project’ (under Project Setup) and ‘Update Project Status’ (under Project Milestone Review) using the app <span><span style="font-weight: bold;">My Projects</span>- <span style="font-weight: bold;">Project Manager</span><span>(F1876)</span></span>as mentioned in 1YF- <span>Project Review</span>test script, using the project from this document</p><p>A possible list of <span style="font-weight: bold;">Milestones</span>can be the following: </p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Example</strong></div><ol><li><p>Concept Review and Approval</p></li><li><p>Final Design Review and Approval</p></li><li><p>Prototype Testing</p></li><li><p>Design Release</p></li></ol></span>
[14 empty] | Upload Planned Costs |  |  |  | Information | <h2>Purpose</h2><div>In this activity, you upload planned costs to Work Packages. <span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>You will be able to use the Cloud Analytics functionality to input planned costs to the project by using the test script for scope item <a href="https://me.sap.com/processnavigator/SolP/2YG" target="_blank" rel="noopener" alt="https://me.sap.com/processnavigator/SolP/2YG" title="https://me.sap.com/processnavigator/SolP/2YG">2YG</a>.</p></span></div><h2>Procedure</h2>
[14 empty] | Upload Planned Costs |  |  |  | Log On | <p>Log on to the SAP Fiori launchpad as a <span>Project Financial Controller</span></p> | <p></p>
[14 empty] | Upload Planned Costs |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Import Financial Plan Data</span> <span>(F1711)</span></span>.</p> | <p>The <span style="font-weight: bold;">Import Financial Plan Data</span> screen is displayed.</p>
[14 empty] | Upload Planned Costs |  |  |  | Download Template; Fill the planned costs in the CSV file | <p>Choose <span style="font-weight: bold;">Download Templates</span>. A pop-up window appears.</p><p>In the pop-up window, choose <span style="font-weight: bold;">,</span> (Comma) from the <span style="font-weight: bold;">Separator for .csv files</span> dropdown and then choose <span style="font-weight: bold;">Project Planning</span>; the template CSV file will be downloaded to the local machine.</p><p>Choose <span style="font-weight: bold;">Close</span>.</p><p>Access / open the file and fill the plan values.</p><p>Make sure to save the file in CSV (Comma delimited) (*.csv) format .</p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Note</strong></div><p>Remember the location of the file stored.</p></span> | <p>CSV file is saved with the plan costs.</p><p></p>
[14 empty] | Upload Planned Costs |  |  |  | Information | <p><span style="font-weight: bold;">Adapt the Project Planning Template</span></p><p>A template table is provided for your reference with sample values as follows:</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"><col width="11.11111111111111%"></colgroup><thead><tr><th><p><span style="font-weight: bold;">Category</span></p></th><th><p><span style="font-weight: bold;">General Ledger Fiscal Year</span></p></th><th><p><span style="font-weight: bold;">Posting Period</span></p></th><th><p><span style="font-weight: bold;">Company Code</span></p></th><th><p><span style="font-weight: bold;">Project Definition</span></p></th><th><p><span style="font-weight: bold;">Work Breakdown Structure Element (WBS Element)</span></p></th><th><p><span style="font-weight: bold;">Account Number</span></p></th><th><p><span style="font-weight: bold;">Amount in Global Currency</span></p></th><th><p><span style="font-weight: bold;">Global Currency</span></p></th></tr></thead><tbody><tr><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td></td><td></td><td></td><td></td></tr><tr><td><p>PLN</p></td><td><p>&lt;current year&gt;</p><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Example</strong></div><p>2018</p></span></td><td><div>&lt;current month&gt;<span aria-labelledby="n3t" style="color: #346187; "><div><strong>Example</strong></div><p>8</p></span></div></td><td><p><span style="font-family:Courier New;">3310</span></p></td><td><p>RnD_00001</p></td><td><p>RnD_000XX_01</p></td><td><p>94311000</p></td><td><p>1000</p></td><td><p>USD</p></td></tr></tbody></table></div>
[14 empty] | Upload Planned Costs |  |  |  | Import Planned Cost Data | <p>Choose <span style="font-weight: bold;">Browse</span>. Select the CSV file from the local system which has the planned cost data already maintained for the project created above.</p><p>Choose <span style="font-weight: bold;">Import Source File</span>.</p> | <p>A message confirms that the import is successful.</p>
[14 empty] | Assign Project Budget |  |  |  | Information | <h2>Purpose</h2><div>In this activity, you post planned budget to Work Package.<span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>You will be able to allocate the project budget following this procedure below or by using the Analytics Cloud functionality to input planned budget to the project by using the test script for scope item <a href="https://me.sap.com/processnavigator/SolP/2YG" target="_blank" rel="noopener" alt="https://me.sap.com/processnavigator/SolP/2YG" title="https://me.sap.com/processnavigator/SolP/2YG">2YG</a>. </p></span></div><h2>Procedure</h2>
[14 empty] | Assign Project Budget |  |  |  | Log On | <p>Log on to the SAP Fiori launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Assign Project Budget |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Import Financial Plan Data</span> <span>(F1711)</span></span>.</p> | <p>The <span style="font-weight: bold;">Import Financial Plan Data</span> screen is displayed.</p>
[14 empty] | Assign Project Budget |  |  |  | Download Template; Fill the planned Budget in the CSV file | <p>Choose <span style="font-weight: bold;">Download Templates</span>. A pop-up window appears.</p><p>In the pop-up window, choose <span style="font-weight: bold;">,</span> (Comma) from the <span style="font-weight: bold;">Separator for .csv files</span> dropdown and then choose <span style="font-weight: bold;">Project Budgeting</span>; the template CSV file will be downloaded to the local machine.</p><p>Choose <span style="font-weight: bold;">Close</span></p><p>Access / open the file and fill the planned Budget values.</p><p>Make sure to save the file in CSV (Comma delimited) (*.csv).</p><div><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Note</strong></div><p>Remember the location of the files stored.</p></span></div> | <p>CSV file will be saved with the budget details.</p>
[14 empty] | Assign Project Budget |  |  |  | Information | <p><span style="font-weight: bold;">Adapt the Project Budget Template</span></p><p>A template table is provided below for your reference with sample values:</p><div><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Note</strong></div><p>The following account is not specific for budget allocation, you can also use a different account for the posting.</p></span></div><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="12.5%"><col width="12.5%"><col width="12.5%"><col width="12.5%"><col width="12.5%"><col width="12.5%"><col width="12.5%"><col width="12.5%"></colgroup><thead><tr><th><p><span style="font-weight: bold;">Category</span></p></th><th><p><span style="font-weight: bold;">General Ledger Fiscal Year</span></p></th><th><p><span style="font-weight: bold;">Posting Period</span></p></th><th><p><span style="font-weight: bold;">Project Definition</span></p></th><th><p><span style="font-weight: bold;">Work Breakdown Structure Element (WBS Element)</span></p></th><th><p><span style="font-weight: bold;">Account Number</span></p></th><th><p><span style="font-weight: bold;">Amount in Global Currency</span></p></th><th><p><span style="font-weight: bold;">Global Currency</span></p></th></tr></thead><tbody><tr><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td><p><span style="font-family:Courier New;">X</span></p></td><td></td><td></td><td></td><td></td></tr><tr><td><p><span style="font-family:Courier New;">BUDGET01</span></p></td><td><p><span style="font-family:Courier New;">&lt;current year&gt;</span></p><p>Example: <span style="font-family:Courier New;">2018</span></p></td><td><p><span style="font-family:Courier New;">&lt;current month&gt;</span></p><p>Example: <span style="font-family:Courier New;">04</span></p></td><td><p><span style="font-family:Courier New;">RnD_00001</span></p></td><td><p><span style="font-family:Courier New;">RnD_00001_01</span></p></td><td><p>Example: <span style="font-family:Courier New;">94311000</span></p></td><td><p><span style="font-family:Courier New;">1000</span></p></td><td><p>USD</p></td></tr></tbody></table></div>
[14 empty] | Assign Project Budget |  |  |  | Import Planned Budget Data | <p>Choose <span style="font-weight: bold;">Browse</span>. Select the CSV file from the local system which already has the planned budget data maintained for the project created above.</p><p>Choose <span style="font-weight: bold;">Import Source File</span>.</p> | <p>A system message tells you that the import is successful.</p>
[14 empty] | Define Demand |  |  |  | Information | <h2>Purpose</h2><p>This activity deals with demand planning activities for the project.</p><h2>Procedure</h2><p>To execute this activity, run the step 'Define Demand' from 4RF- <span>Project Control – Resourcing and Procurement</span>test script to create project related demands</p>
[14 empty] | Release Project |  |  |  | Information | <h2>Purpose</h2><div>In this activity, you release the Project.<span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>To use the workflow for the project release approval process, perform the steps described in<cite>Review Workflow for the Release of a Project (Optional)</cite>of the<cite>Project Review (1YF)</cite>test script, using the project from this document.</p></span></div><h2>Procedure</h2>
[14 empty] | Release Project |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Release Project |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Project Control - Enterprise Projects</span> <span>(F3215)</span></span></p> | <p>The <span style="font-weight: bold;">Project Control</span> screen is displayed.</p>
[14 empty] | Release Project |  |  |  | Open Project | <p>In the Standard section, make the following entries and choose <span style="font-weight: bold;">Go</span>. </p><p><span style="font-weight: bold;">Project</span> : &lt;Refer the respective Project created in the chapter 'Create Project '&gt;</p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Example</strong></div><p>RnD_00001 (for R &amp; D Projects) </p></span> | <p>At least one entry is displayed in the Worklist area.</p>
[14 empty] | Release Project |  |  |  | Release Project and Structure | <p>Select the project and in header section choose <span style="font-weight: bold;"> Processing Status &gt; Release</span></p> | <p>Project status is changed to Released.</p><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Note</strong></div><ul><li><p>You can also use the <span style="font-weight: bold;">Change Processing status </span>using the <span style="font-weight: bold;">Project Briefs</span> app in the role of <span style="font-weight: bold;">Project Manager </span> .</p></li><li><p>Project once released cannot be renamed or deleted</p></li></ul></span>
[14 empty] | Release Project |  |  |  | Maintain actual start date in WBS Elements | <p>Choose <span><span><span style="font-weight: bold;">Related Apps</span> <span style="font-weight: bold;">Project Planning</span></span></span> . Choose <span style="font-weight: bold;">Edit</span> to open the project in change mode.</p><p>For all created WBS elements, maintain <span style="font-weight: bold;">Actual Start Date</span> field in <span style="font-weight: bold;">in WBS Element Detailed Overview</span> page</p><p>Choose <span style="font-weight: bold;">Save</span>.</p> | <p>Project is saved with the Actual start dates for WBS elements.</p>
[14 empty] | Time Recording |  |  |  | Information | <h2>Purpose</h2><p>In this activity, employee enters the time recording for WBS Element via Manage My Time Sheet application.</p><h2>Procedure</h2><div>To execute this activity, execute 1Q4 - <span>Time Recording</span>test script, using the WBS Element from this document.<span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>While creating the task, maintain the <span style="font-weight: bold;">Activity Type</span>as <span style="font-family:Courier New;">11</span>and WBS element created in the Create Project step of this document.</p></span></div><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="25%"><col width="25%"><col width="25%"><col width="25%"></colgroup><thead><tr><th><p><span style="font-weight: bold;">Data</span></p></th><th><p><span style="font-weight: bold;">Sample Value</span></p></th><th><p><span style="font-weight: bold;">Details</span></p></th><th><p><span style="font-weight: bold;">Comments</span></p></th></tr></thead><tbody><tr><td><p>WBS Element</p></td><td><p><span style="font-family:Courier New;">&lt;RnD_00001.03&gt;</span></p></td><td><p><span style="font-family:Courier New;">&lt;WBS for Prototype Phase &gt;</span></p></td><td><p></p></td></tr></tbody></table></div>
[14 empty] | Project Demand |  |  |  | Information | <h2>Purpose</h2><p>This activity deals with planning demand activities for the project.</p><h2>Procedure</h2><p>To execute this activity, run steps from 4RF- <span>Project Control – Resourcing and Procurement</span>test script to create and process your project related demands.</p>
[14 empty] | Project Control - Procurement |  |  |  | Information | <h2>Purpose</h2><p>This activity deals with demand planning and consumable purchasing activities for the project.</p><h2>Procedure</h2><p>To execute this activity, run steps from 4RF- <span>Project Control – Resourcing and Procurement</span>test script to process your purchase requisitions generated from project demand.</p>
[14 empty] | Post General Journal Entries |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you post actual primary costs to WBS Elements.</p><h2>Procedure</h2>
[14 empty] | Post General Journal Entries |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>General Ledger Accountant</span>.</p> | <p></p>
[14 empty] | Post General Journal Entries |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Post General Journal Entries</span> <span>(F0718)</span></span>.</p> | <p>The <span style="font-weight: bold;">Post General Journal Entries</span> screen is displayed.</p>
[14 empty] | Post General Journal Entries |  |  |  | Enter General Journal Entries | <p>On the <span style="font-weight: bold;">Post General Journal Entries</span> screen, make the following entries:</p><p><span style="font-weight: bold;">Journal Entry Date</span>: <span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Posting Date</span>: <span style="font-family:Courier New;">Today</span></p><p><span style="font-weight: bold;">Journal Entry Type: </span><span style="font-family:Courier New;">SA</span></p><p><span style="font-weight: bold;">Company Code: </span><span style="font-family:Courier New;">3310</span></p><p><span style="font-weight: bold;">Transaction Currency: </span><span style="font-family:Courier New;">AED</span></p><p>In the <span style="font-weight: bold;">Line Items</span> area, make the following entries and choose <span style="font-family:Courier New;">Enter</span><span style="font-weight: bold;">:</span></p><p><span style="font-weight: bold;">Line Item 1</span></p><p><span style="font-weight: bold;">G/L Account: </span><span style="font-family:Courier New;">61003000</span> or <span style="font-family:Courier New;">50305000</span> or <span style="font-family:Courier New;">51100000</span></p><p><span style="font-weight: bold;">Debit: </span><span style="font-family:Courier New;">1000</span></p><p><span style="font-weight: bold;">Credit: </span><span style="font-family:Courier New;">0</span></p><p>Choose <span style="font-weight: bold;">Expand All</span>.</p><p><span style="font-weight: bold;">Tax Code:</span><span style="font-family:Courier New;">&lt;Input Tax Code&gt;</span></p><p><span style="font-weight: bold;">WBS Element: </span><span style="font-family:Courier New;">&lt;Enter the WBS Element&gt;</span></p><p><span style="font-weight: bold;">Line Item 2</span></p><p><span style="font-weight: bold;">G/L Account:</span><span style="font-family:Courier New;">10010000</span></p><p><span style="font-weight: bold;">Debit: </span><span style="font-family:Courier New;">0</span></p><p><span style="font-weight: bold;">Credit: </span><span style="font-family:Courier New;">1000</span></p><p>Choose <span style="font-weight: bold;">Post</span></p><span aria-labelledby="n0t" style="color: #9f0000;"><div><strong>Caution</strong></div><p>In case pro-rata VAT is relevant for you, please make sure you meet the prerequisites as mentioned in chapter 2. </p></span> | <p>Check that <span style="font-weight: bold;">Total Balance</span> is 0.00</p>
[14 empty] | Post General Journal Entries |  |  |  | Optional: Batch upload general Journal entries | <p><span style="font-weight: bold;">Download Template file to local:</span></p><p>On the <span style="font-weight: bold;">Post General Journal Entries</span> screen, choose <span style="font-weight: bold;">Upload New Entry</span>.</p><p>On the <span style="font-weight: bold;">Upload General Journal Entries </span>screen. Choose <span style="font-weight: bold;">Download Template</span>.</p><p>On the Template Download pop-up window, make the following entries, then choose <span style="font-weight: bold;">Download</span>.</p><p><span style="font-weight: bold;">Template Language: </span><span style="font-family:Courier New;">Arabic</span></p><p><span style="font-weight: bold;">Format: </span><span style="font-family:Courier New;">MS Excel Workbook (*.xlsx)</span></p><p>Download the template file to the local and fill general journal entries according to the template.</p><p><span style="font-weight: bold;">Upload Template file and batch upload general journal entries</span>:</p><p>On the <span style="font-weight: bold;">Post General Journal Entries</span> screen, choose <span style="font-weight: bold;">Upload New Entry</span>.</p><p>On the <span style="font-weight: bold;">Upload General Journal Entries </span>screen, choose <span style="font-weight: bold;">Browse</span>.</p><p>On the pop-up screen, choose your local filled out template file and upload it.</p><p>A system message tells you that the held journal entries have been updated.</p><p>Check batch upload general journal entries.</p> | <p>The General Journal Entries are posted.</p>
[14 empty] | Post General Journal Entries |  |  |  | Post General Journal Entries | <p>Choose <span style="font-weight: bold;">Post</span>.</p> | <p>A success message appears displaying the document number.</p>
[14 empty] | Monitor Projects |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you can analyze the costs (planned/actual) recorded on the project using different tiles available on the Fiori launchpad. You can also check project progress and the overall status of your project.</p>
[14 empty] | Monitor Notification (Optional) |  |  |  | Information | <h2>Procedure</h2>
[14 empty] | Monitor Notification (Optional) |  |  |  | Log on | <p>Log on to the SAP Fiori launchpad as a <span>Project Financial Controller</span>.</p>
[14 empty] | Monitor Notification (Optional) |  |  |  | Choose the notifications | <p>Choose the <span style="font-weight: bold;">Notifications</span> icon at the top right of the <span style="font-weight: bold;">Home</span> screen.</p><p>Choose the notifications which are generated by the system.</p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>This notification will be displayed only in case there is a situation of actual postings exceeding the budget threshold limit set in the AVC profile selected for the project.</p></span> | <p>The <span style="font-weight: bold;">Project Budget Report-Overview</span> screen is displayed.</p>
[14 empty] | Monitor Notification (Optional) |  |  |  | Detailed information from notifications | <ol><li><p>Open <span><span style="font-weight: bold;">Project Control - Enterprise Projects</span> <span>(F3215)</span></span>.</p></li><li><p>In the <span style="font-weight: bold;">Standard</span> section, make the following entry and choose <span style="font-weight: bold;">Go</span>:</p><ul><li><p><span style="font-weight: bold;">Project</span>: &lt;Refer the Project mentioned in the notification&gt;</p></li></ul></li><li><p>Select the project from the displayed list and click to open. </p><p>The <span style="font-weight: bold;">Situations</span> section of the project is displayed and information like the actual posting date and the WBS, to which the postings are made, is displayed. </p><p>You can also see the list of notifications from the situation management that got triggered against the project by clicking on the drop-down arrow in the notification.</p></li></ol> | <p>Detailed information of the situation is displayed.</p>
[14 empty] | Monitor Notification (Optional) |  |  |  | Actions in notifications | <div>You can choose to dismiss the notification by selecting one of the following actions:<ul><li><p>Situation Resolved</p></li><li><p>Situation Obsolete</p></li><li><p>Situation Invalid</p></li></ul></div><p>Once the situation is dismissed, no one can see the situation. </p> | <p>Situation is dismissed by selecting the appropriate option.</p>
[14 empty] | Monitor Projects via Project Financial Controller Overview |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you analyze the status, timelines, budget and costs of project.</p><div>: <span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>You will be able to access the reports such as Project Cost,Plan vs Actual, Project Budget Report and Monitor Projects directly from Project Financial Overview.</p></span></div><h2>Procedure</h2>
[14 empty] | Monitor Projects via Project Financial Controller Overview |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Monitor Projects via Project Financial Controller Overview |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Project Financial Controller Overview</span> <span>(F3078)</span></span></p> | <p>The <span style="font-weight: bold;">Project Financial Controller Overview</span> screen is displayed.</p>
[14 empty] | Monitor Projects via Project Financial Controller Overview |  |  |  | Enter Selection Criteria | <p>In the standard section, make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Planning Category</span>: <span style="font-family:Courier New;">PLN</span>.</p> | <p>Projects with selected planning category are displayed in the <span style="font-weight: bold;">Data Analysis</span> area.</p>
[14 empty] | Monitor Projects via Project Financial Controller Overview |  |  |  | Check Financials | <p>Check Financials and Overall status of the project using various cards.</p> | <p>The Overall Status, Planned and Active Projects, Actual costs, Cost to Date, Timeline and Upcoming Milestone are displayed.</p>
[14 empty] | Monitor Projects via Monitor Projects App |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you analyze the cost and overall progress of your project.</p><h2>Procedure</h2>
[14 empty] | Monitor Projects via Monitor Projects App |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Monitor Projects via Monitor Projects App |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Monitor Projects</span> <span>(F3088)</span></span></p> | <p>The <span style="font-weight: bold;">Monitor Projects</span> screen is displayed.</p>
[14 empty] | Monitor Projects via Monitor Projects App |  |  |  | Enter Selection Criteria | <p>In the upper area, make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Project: </span><span style="font-family:Courier New;">RnD_00001</span></p><p><span style="font-weight: bold;">Planning Category</span>: <span style="font-family:Courier New;">PLN</span></p> | <p>At least one entry is shown in the Worklist display area.</p>
[14 empty] | Monitor Projects via Monitor Projects App |  |  |  | Check Financials | <p>From the Worklist area, select the project and choose <span style="font-weight: bold;">View Costs </span>to check project costs.</p> | <p><span style="font-weight: bold;">Project Costs</span> report of the selected project is displayed</p>
[14 empty] | Monitor Projects via Monitor Projects App |  |  |  | Check Project Progress | <p>From the Worklist area, select the project and choose <span style="font-weight: bold;">Project Progress </span>to go to the <span style="font-weight: bold;">Monitor Project Progress</span> screen which shows the project timelines.</p> | <p>A detailed view of project progress is displayed in graphical form</p>
[14 empty] | Monitor Projects via Project Cost Report |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you analyze the cost structure of your project and check planned cost.</p><h2>Procedure</h2>
[14 empty] | Monitor Projects via Project Cost Report |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Monitor Projects via Project Cost Report |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Project Cost Report</span> - <span style="font-weight: bold;">Plan/Actual</span> <span>(F2513)</span></span></p> | <p>The <span style="font-weight: bold;">Project Cost </span>screen is displayed.</p>
[14 empty] | Monitor Projects via Project Cost Report |  |  |  | Enter Selection Criteria | <p>In the upper area, make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Project</span>: <span style="font-family:Courier New;">RnD_00001</span></p><p><span style="font-weight: bold;">Planning Category 1</span>: <span style="font-family:Courier New;">Plan</span></p><p><span style="font-weight: bold;">Planning Category 2</span>: <span style="font-family:Courier New;">CPM Baseline</span></p> | <p>Details of the project structure and the corresponding Plan and Actual costs as well as commitments are displayed.</p>
[14 empty] | Monitor Projects via Project Cost Report |  |  |  | Navigation to Project Cost Report – Line items; view details of different cost | <p>Select the project in the table, and choose <span style="font-weight: bold;">View Details</span>.</p><p>On <span style="font-weight: bold;">Project Costs - line items</span> screen, check financials using drilldown and filter possibilities.</p> | <p>All Plan and Actual costs are displayed.</p>
[14 empty] | Monitor Projects via Project Budget Report |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you analyze the cost structure of your project and check planned budget.</p><h2>Procedure</h2>
[14 empty] | Monitor Projects via Project Budget Report |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Monitor Projects via Project Budget Report |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Project Budget Report</span> <span>(F3377)</span></span></p> | <p>The <span style="font-weight: bold;">Project Cost </span>screen is displayed.</p>
[14 empty] | Monitor Projects via Project Budget Report |  |  |  | Enter Selection Criteria | <p>In the upper area, make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Project</span>: <span style="font-family:Courier New;">RnD_00001</span></p><p><span style="font-weight: bold;">Planning Category 1</span><span style="font-family:Courier New;">:Plan</span></p><p><span style="font-weight: bold;">Fiscal Year:</span><span style="font-family:Courier New;"> Current year</span></p> | <div>Details of the project structure and the corresponding planned budget are displayed. <span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>The Aggregated and Non Aggregated Costs of the selected project are displayed.</p><p>In the budget report, you will see the Assigned Value (commitment +Actual) and Available budget (Budget-Assigned Value), based on which you can analyze the project.</p></span></div>
[14 empty] | Monitor Projects via Project Budget Report |  |  |  | Navigation to Project Budget Report – Line items; view details of different cost | <p>Select the project in the table, and choose <span style="font-weight: bold;">View Details</span>.</p><div>On the <span style="font-weight: bold;">Project Budget Report- line items</span> screen, check financials using drilldown and filter possibilities.<span aria-labelledby="n1t" style="color: #346187; "><div><strong>Note</strong></div><p>In the <span style="font-weight: bold;">Standard</span> section, the information is shown in the <span style="font-weight: bold;">Compact Filter</span> view by default.</p><p>You can also change it to <span style="font-weight: bold;">Visual Filter</span> view to get an easy understanding of overall costs of the project. </p><p>This visual depiction helps the stakeholders to get an overview of the project</p></span></div> | <p>All Plan, Actual and Budget costs are displayed.</p>
[14 empty] | Monitor Projects via Project Budget Report |  |  |  | Navigation to Project Budget Report- Line items: view graphical representation of different costs | <p>In the <span style="font-weight: bold;">Project Budget Report - Line items</span> screen, you will see the different cost items recorded on the project as graphical representations, such as the bubble chart, bar graph and pie chart. </p><span aria-labelledby="n2t" style="color: #346187; "><div><strong>Note</strong></div><p>You can see the details of the cost items by hovering the cursor on the graphs.</p></span> | <p>The Cumulative Actual costs, Commitments and Budget posted on the project are displayed.</p>
[14 empty] | Monitor Projects via Manage Project Procurement |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you monitor the purchasing documents via the Manage Project Procurement app and check net order value or ordered quantity for purchase order or purchase requisitions assigned to the project.</p><h2>Procedure</h2>
[14 empty] | Monitor Projects via Manage Project Procurement |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Monitor Projects via Manage Project Procurement |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Manage Project Procurement</span> <span>(F2930)</span></span></p>
[14 empty] | Monitor Projects via Manage Project Procurement |  |  |  | Enter Selection Criteria | <p>In the upper area, make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Project</span>: <span style="font-family:Courier New;">&lt;Enter the Project&gt;</span></p><p><span style="font-weight: bold;">Display currency :</span><span style="font-family:Courier New;">AED</span></p><p><span style="font-weight: bold;">PO Delivery Status :</span><span style="font-family:Courier New;">Open</span></p> | <div>Details of the project related to purchase order and purchase requisition such as the following are displayed according to selection : <ul><li><p>delivery quantity</p></li><li><p>net order value</p></li><li><p>delivery date and so on</p></li></ul></div><p>You can click on each link to get more information.</p>
[14 empty] | Monitor Projects via P&amp;L Plan/Actual |  |  |  | Information | <h2>Purpose</h2><p>In this activity, you analyze the cost structure of your PS Project and compare actual vs planned.</p><h2>Procedure</h2>
[14 empty] | Monitor Projects via P&amp;L Plan/Actual |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Monitor Projects via P&amp;L Plan/Actual |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">P&amp;L Plan/Actual</span> - <span style="font-weight: bold;">Profit and Loss</span> <span>(F1710)</span></span>(F1710)</p> | <p>The <span style="font-weight: bold;">P&amp;L Plan/Actual</span> screen is displayed.</p>
[14 empty] | Monitor Projects via P&amp;L Plan/Actual |  |  |  | Enter Selection Criteria | <p>In the upper area, make the following entries and choose <span style="font-weight: bold;">Go</span>.</p><p><span style="font-weight: bold;">Ledger: </span><span style="font-family:Courier New;">0L</span></p><p><span style="font-weight: bold;">Ledger Fiscal Year</span>: <span style="font-family:Courier New;">Current year</span></p><p><span style="font-weight: bold;">Planning Category</span>: <span style="font-family:Courier New;">PLN</span></p><p><span style="font-weight: bold;">Project definition</span>: <span style="font-family:Courier New;">&lt;Enter the Project Definition&gt;</span></p> | <p>At least one entry is shown in the <span style="font-weight: bold;">Data Analysis</span> area.</p>
[14 empty] | Monitor Projects via P&amp;L Plan/Actual |  |  |  | Check Financials | <p>Check financials using drilldown and filter possibilities.</p> | <p>All actual costs are displayed.</p>
[14 empty] | Period-End Closing Projects |  |  |  | Information | <h2>Purpose</h2><p>In this activity, the <span>Project Financial Controller</span>records the percentages of actual overheads on the project, generates the settlement rule and settles the actuals on the project. </p><h2>Procedure</h2><p>To execute this activity, the <span>Project Financial Controller</span>performs the step ‘Run Actual Overhead-Projects’ and 'Period-End Process: Internal Cost Projects ' as mentioned in BNA - <span>Period-End Closing – Projects</span>test script, using the WBS Element from this document.</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="25%"><col width="25%"><col width="25%"><col width="25%"></colgroup><thead><tr><th><p><span style="font-weight: bold;">Data</span></p></th><th><p><span style="font-weight: bold;">Sample Value</span></p></th><th><p><span style="font-weight: bold;">Details</span></p></th><th><p><span style="font-weight: bold;">Comments</span></p></th></tr></thead><tbody><tr><td><p>WBS Element</p></td><td><p><span style="font-family:Courier New;">&lt;</span><span style="font-family:Courier New;">RnD_000XX.03&gt;</span></p></td><td><p><span style="font-family:Courier New;">&lt;WBS for Prototype Phase&gt;</span></p></td><td><p></p></td></tr></tbody></table></div>
[14 empty] | Close Project |  |  |  | Information | <h2>Context</h2><p>In this activity, <span>Project Financial Controller</span>close the completed project.</p><h2>Procedure</h2>
[14 empty] | Close Project |  |  |  | Log On | <p>Log on to the SAP Fiori Launchpad as a <span>Project Financial Controller</span>.</p> | <p></p>
[14 empty] | Close Project |  |  |  | Access App | <p>Open <span><span style="font-weight: bold;">Project Control - Enterprise Projects</span> <span>(F3215)</span></span></p> | <p>The <span style="font-weight: bold;">Project Control</span> screen is displayed.</p>
[14 empty] | Close Project |  |  |  | Open Project | <p>In the Standard section, make the following entries and choose <span style="font-weight: bold;">Go</span>. </p><p><span style="font-weight: bold;">Project</span> : &lt;Refer the respective Project created in the chapter 'Create Project '&gt;</p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Example</strong></div><p>RnD_00001 (for R &amp; D Projects) </p></span> | <p>At least one entry is displayed in the Worklist area.</p>
[14 empty] | Close Project |  |  |  | Complete Project Parts and Project | <p>Select the Project and in header section choose <span style="font-weight: bold;">Processing Status</span> and choose <span style="font-weight: bold;">Complete</span></p> | <p>Project is saved with status Completed. (The system status is set to Technically Complete)</p>
[14 empty] | Close Project |  |  |  | Close Project and Structure | <p>Select the Project and in header section choose <span style="font-weight: bold;">Processing Status</span> and choose <span style="font-weight: bold;">Close</span></p> | <p>Project is saved with status <span style="font-weight: bold;"> Closed.</span> .</p>
[14 empty] | Additional Information |  |  |  | Information | <h1>Appendix</h1><h1>Process Integration</h1><h1>Preceding Processes</h1><h1>Succeeding Processes</h1>