## Test Cases
# | This file is a template you can use to manually upload the test script as test case in SAP Cloud ALM. For more information, refer to SAP Note 3217691.
# | Any changes you make to the values of columns marked with [---] will be ignored.
# | 3KX_S4CLD2608_BPD_EN_XX (2026-06-15 08:24:51)
Test Case GUID | Test Case Name* | [Scope GUID] | [Scope Name] | [Solution Process GUID] | [Solution Process Name] | [Solution Process Flow GUID] | [Solution Process Flow Name] | [Solution Process Flow Diagram GUID] | [Solution Process Flow Diagram Name] | [Test Case Priority] | [Test Case Owner] | Test Case Status | Activity GUID | Activity Title* | Activity Target Name | Activity Target URL | Action GUID | Action Title* | Action Instructions* | Action Expected Result
| Privacy Risk Detection with SAP Risk and Assurance Management (3KX) | [10 empty] | In Preparation |  | Additional Information |  |  |  | Information | <h1>Purpose</h1><h2>Overview</h2><p>With SAP Risk and Assurance Management data protection and privacy controls, SAP establishes effective means to analyze and detect data protection and privacy anomalies in your connected <span>SAP S/4HANA Cloud Public Edition</span>system.</p><p>The use of personal information is strictly regulated by various regulations. Privacy risks exist when this type of data is collected and processed. As a supplement to manual governance, this scope item enables the automatic detection of privacy risks for personnel information and relevant documents (such as sales orders), providing insights on regulatory reporting and proactive auditing.</p>This document provides a general procedure for testing the scope item after solution activation. Detection of privacy risks in sales order is taken as an example in this test script. Besides, you can also implement other use cases based on your requirements. Please refer to Use Cases for more details. <h1>Use Cases</h1><p>SAP Risk and Assurance Management provides pre-defined business content, such as controls, automated procedures. They can be used as a quick start of your business as well as for demo and education purpose.</p><p>For more information on pre-defined business content, please refer to the <em>Business Content</em>section in this <a href="https://help.sap.com/spg" target="_blank" rel="noopener" alt="https://help.sap.com/spg" title="https://help.sap.com/spg">document</a>.</p><h1>Prerequisites</h1>This section summarizes all the prerequisites for conducting the test in terms of systems, users, master data, organizational data, other test data and business conditions.<h1>Additional Manual Configuration</h1>Before you can test this scope item, you must have completed the additional configuration steps that are described in the <em>Set-Up Instructions</em> for this scope item. These configuration steps are specific for your implementation and include mandatory settings that are not delivered by SAP and must be created by you. For more information, follow the link to the document: <a href="https://help.sap.com/docs/SAP_S4HANA_BEST_PRACTICES/1c43a73b798538647d39951fc1313029" target="_blank" rel="noopener" alt="https://help.sap.com/docs/SAP_S4HANA_BEST_PRACTICES/1c43a73b798538647d39951fc1313029" title="https://help.sap.com/docs/SAP_S4HANA_BEST_PRACTICES/1c43a73b798538647d39951fc1313029">Link to Set-Up Instructions</a><h1>System Access</h1><p>Before this scope item can be tested, you must have access to SAP Risk and Assurance Management system and finish the onboarding process of SAP Risk and Assurance Management.</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="28.333333333333332%"><col width="71.66666666666667%"></colgroup><thead><tr><th><p>System</p></th><th><p>Details</p></th></tr></thead><tbody><tr><td><p>SAP Risk and Assurance Management</p></td><td><p>Accessible via SAP Risk and Assurance Management Fiori launchpad. Your system administrator provides you with the URL to access the various apps assigned to your role.</p></td></tr></tbody></table></div><h1>Roles</h1><p>In SAP Risk and Assurance Management:</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="33.333333333333336%"><col width="33.333333333333336%"><col width="33.333333333333336%"></colgroup><thead><tr><th><p>Business Role</p></th><th><p>Role Collection</p></th><th><p>Log On</p></th></tr></thead><tbody><tr><td><p>Specialist</p></td><td><p>compliance_specialist</p></td><td><p>Please ask your system administrator to assign to the tester.</p></td></tr><tr><td><p>Manager</p></td><td><p>compliance_manager </p></td><td><p>Please ask your system administrator to assign to the tester.</p></td></tr></tbody></table></div><p>For more information, please refer to <cite>User and Authorization Management</cite>in this <a href="https://help.sap.com/viewer/9f06df5970b84ee18b9aa33c8fb0e4bd/1.0.0.0/en-US" target="_blank" rel="noopener" alt="https://help.sap.com/viewer/9f06df5970b84ee18b9aa33c8fb0e4bd/1.0.0.0/en-US" title="https://help.sap.com/viewer/9f06df5970b84ee18b9aa33c8fb0e4bd/1.0.0.0/en-US">document</a>.</p><h1>Master Data, Organizational Data, and Other Data</h1><p>The organizational structure and master data of your company have been created in your system during activation. The organizational structure reflects the structure of your company. The master data represent materials, business partners, depending on the operational focus of your company.</p><h1>Business Conditions</h1><p>Before this scope item can be tested, the following business conditions must be met.</p><div><table summary="" frame="border" border="1" rules="all"><colgroup><col width="25%"><col width="75%"></colgroup><thead><tr><th><p>Scope Item</p></th><th><p>Business Condition</p></th></tr></thead><tbody><tr><td><p>1KA - <span>Information Lifecycle Management</span></p></td><td><p>Information lifecycle management has been activated and retention rules has been maintained for the relevant objects such as sales order and HR objects. </p><p>For example, if you want to detect privacy risk in sales order, you need to assign ILM object SD_VBAK to the appropriate existing audit area or a new one. Then create ILM policy and maintain retention rules under this combination of audit area and ILM object. </p></td></tr></tbody></table></div>
[14 empty] | Test Procedures |  |  |  | Information | This section describes test procedures for each process step that belongs to this scope item.
[14 empty] | Create Automated Procedure |  |  |  | Information | <h2>Purpose</h2><p>The compliance specialist creates a new Automated Procedure (AP) to retrieve data in S/4HANA Cloud. This new AP is mandatory for the following Control creation.</p><h2>Prerequisite</h2><p>Before you start creating a new Automated Procedure, make sure the setup guide of this scope item has been followed through to ensure connectivity between SAP Risk and Assurance Management and S/4HANA Cloud. What’s more, make sure the baseline content packages are imported successfully during your onboarding for SAP Risk and Assurance Management.</p><h2>Procedure</h2>
[14 empty] | Create Automated Procedure |  |  |  | Log on | <p>Log on to SAP Risk and Assurance Management as Specialist.</p>
[14 empty] | Create Automated Procedure |  |  |  | Option One: Adjust and Activate Pre-delivered Automated Procedure | <p>Open the <span style="font-weight: bold;">Manage Automated Procedures</span> tile.</p><p>Select a pre-delivered <span style="font-weight: bold;">Automated Procedure</span>, for example, <span style="font-weight: bold;">Check sales orders against ILM retention rules</span>, and drill down to the detailed page.</p><p>Choose <span style="font-weight: bold;">Edit</span> on the upper right part of the screen.</p><p>In the <span style="font-weight: bold;">Systems</span> section, choose <span style="font-weight: bold;">Add</span> under <span style="font-weight: bold;">Systems</span> to add the appropriate destination.</p><p>In the <span style="font-weight: bold;">Time-Related Settings</span> section, verify and adjust the <span style="font-weight: bold;">Time-Related Settings</span> which will be used as a criteria when retrieving data.</p><p>Choose <span style="font-weight: bold;">Save and Activate</span> to activate the Standard Automated Procedure.</p> | <p>Standard Automated Procedure is activated successfully.</p>
[14 empty] | Create Automated Procedure |  |  |  | Option Two: Create Your Own Automated Procedure | <p>Open the <span style="font-weight: bold;">Manage Automated Procedures</span> tile.</p><p>On the upper right of the <span style="font-weight: bold;">Procedures List</span>, choose <span style="font-weight: bold;">Create</span>.</p><p>In the <span style="font-weight: bold;">HEADER</span> section, fill in the following details:</p><p><span style="font-weight: bold;">Procedure Name</span>: <span style="font-family:Courier New;">&lt;Enter as appropriate, for example, ZAP_SO&gt;</span></p><p><span style="font-weight: bold;">System Type</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list&gt;</span></p><p><span style="font-weight: bold;">Destination</span>: <span style="font-family:Courier New;">&lt;Select from value help&gt;</span></p><p><span style="font-weight: bold;">Source Type</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list&gt;</span></p><p><span style="font-weight: bold;">OData Service Name</span>: <span style="font-family:Courier New;">/sap/opu/odata/sap/GRCSPG_BASELINE_CONTENT_SRV</span></p><p><span style="font-weight: bold;">OData Entity Set Name</span>: <span style="font-family:Courier New;">&lt;Enter as appropriate, for example, SalesOrderSet&gt;</span></p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>For available pre-delivered OData Entity Set, you can refer to the chapter: Use Cases.</p></span><p>In the <span style="font-weight: bold;">DESCRIPTION</span> section, enter as appropriate.</p><p>Choose <span style="font-weight: bold;">Save</span>. Then choose <span style="font-weight: bold;">Edit</span> .</p><p>In the <span style="font-weight: bold;">Time-Related Settings</span> section, fill in the following details:</p><p><span style="font-weight: bold;">Reference Period</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, Calendar Date&gt;</span></p><p><span style="font-weight: bold;">Field for Time Selection</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, Created On&gt;</span></p><p>In the <span style="font-weight: bold;">Parameters</span> section, choose <span style="font-weight: bold;">Add</span> to add other fields as additional input parameters and then choose <span style="font-weight: bold;">Select</span>.</p><p>Choose <span style="font-weight: bold;">Save and Activate</span> to activate the newly created procedure.</p> | <p>New Automated Procedure is created and activated successfully.</p>
[14 empty] | Create Control |  |  |  | Information | <h2>Purpose</h2><p>The compliance specialist creates a new Control or use the pre-delivered standard Control to include Automated Procedure. It is mandatory for the following Work Package creation.</p><h2>Prerequisite</h2><p>Before you start creating a new Control, make sure the newly created Automated Procedure in the prior steps is activated successfully.</p><h2>Procedure</h2>
[14 empty] | Create Control |  |  |  | Log on | <p>Log on to SAP Risk and Assurance Management as Manager.</p>
[14 empty] | Create Control |  |  |  | Option One: Assign Automated Procedure to Standard Control | <p>Open the <span style="font-weight: bold;">Manage Controls</span> tile.</p><p>Select a pre-delivered <span style="font-weight: bold;">Control</span>, for example, <span style="font-weight: bold;">Sales orders get destroyed when their retention period expires</span>, and drill down to the detailed page.</p><p>Choose <span style="font-weight: bold;">Edit</span>, and then navigate to the <span style="font-weight: bold;">Procedures</span> tab. </p><p>Choose <span style="font-weight: bold;">Add</span> in the <span style="font-weight: bold;">Automated Procedures</span> section.</p><p>Search and select the Automated Procedure created in previous step, then choose <span style="font-weight: bold;">OK</span>.</p><p>Choose <span style="font-weight: bold;">Define</span> under the <span style="font-weight: bold;">Destination</span> column to define the Destinations for the Procedures.</p><p>Choose <span style="font-weight: bold;">Edit</span> in the <span style="font-weight: bold;">Destinations and Parameters</span> view, fill in the input parameters and choose <span style="font-weight: bold;">Save</span>.</p><p>Choose <span style="font-weight: bold;">Activate</span> to activate the Control.</p> | <p>Automated Procedure is assigned to Standard Control.</p>
[14 empty] | Create Control |  |  |  | Option Two: Create Your Own Control | <p>Open the <span style="font-weight: bold;">Manage Controls</span> tile.</p><p>On the upper right of the <span style="font-weight: bold;">Controls List</span>, choose <span style="font-weight: bold;">Create</span> and fill in the following details:</p><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">&lt;Enter as appropriate, for example, ZControl_SO&gt;</span></p><p><span style="font-weight: bold;">Valid From</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, today&gt;</span></p><p><span style="font-weight: bold;">Valid To</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, the end of current month&gt;</span></p><p><span style="font-weight: bold;">Significance</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list, for example, Standard&gt;</span></p><p><span style="font-weight: bold;">Control Risk Level</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list, for example, Medium&gt;</span></p><p><span style="font-weight: bold;">Recommended Monitoring Frequency</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list, for example, Any Frequency&gt;</span></p><p>Choose the <span style="font-weight: bold;">Description</span> tab, enter as appropriate.</p><p>Choose the <span style="font-weight: bold;">Procedures</span> tab, and choose <span style="font-weight: bold;">Add</span> in the <span style="font-weight: bold;">Automated Procedures</span> section.</p><p>Select the Automated Procedure created in the previous step and then choose <span style="font-weight: bold;">OK</span>.</p><p>Choose <span style="font-weight: bold;">Define</span> under the <span style="font-weight: bold;">Destination</span> column to define the Destinations for the Procedures.</p><p>Choose <span style="font-weight: bold;">Edit</span> in the <span style="font-weight: bold;">Destinations and Parameters</span> view, fill in the input parameters and choose <span style="font-weight: bold;">Save</span>.</p><p>Choose <span style="font-weight: bold;">Create</span>, and then choose <span style="font-weight: bold;">Activate</span> to activate the Control.</p> | <p>Your Own Control is created with Automated Procedure assigned. </p>
[14 empty] | Create Work Package |  |  |  | Information | <h2>Purpose</h2><p>The compliance specialist creates a new Work Package to include Control and schedule regular automatic job for the privacy risk detection. </p><h2>Prerequisite</h2><p>Before you start creating a new Work Package, make sure the newly created Control in the prior steps is created successfully and assigned the right target destination system.</p><h2>Procedure</h2>
[14 empty] | Create Work Package |  |  |  | Log on | <p>Log on to SAP Risk and Assurance Management as Specialist.</p>
[14 empty] | Create Work Package |  |  |  | Create Work Package | <p>Open the <span style="font-weight: bold;">Manage Work Packages</span> tile.</p><p>On the upper right of the <span style="font-weight: bold;">Packages List</span>, choose <span style="font-weight: bold;">Create</span> and then choose <span style="font-weight: bold;">Control Performance</span>.</p> | <p><span style="font-weight: bold;">New Work Package</span> page is displayed on the right part of the screen.</p>
[14 empty] | Create Work Package |  |  |  | Enter Information for New Work Package | <p>In the <span style="font-weight: bold;">General Information</span> section, fill in the following details:</p><p><span style="font-weight: bold;">Name</span>: <span style="font-family:Courier New;">&lt;Enter as appropriate, for example, ZWP_SO&gt;</span></p><p><span style="font-weight: bold;">Reference Period</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list, for example, Calendar Date&gt;</span></p><span aria-labelledby="n0t" style="color: #346187; "><div><strong>Note</strong></div><p>Like <span style="font-weight: bold;">Reference Period</span> in Automatic Procedure, there are three types of reference period: <span style="font-weight: bold;">Calendar Date</span>, <span style="font-weight: bold;">Fiscal Period</span>, and <span style="font-weight: bold;">No Date</span>. The <span style="font-weight: bold;">Reference Period</span> selected must be consistent with the value selected in the Automatic Procedure created in previous step. For example, select <span style="font-weight: bold;">Calendar Date</span>.</p></span><p><span style="font-weight: bold;">Start Date</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, today&gt;</span></p><p><span style="font-weight: bold;">End Date</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, No End Date&gt;</span></p><p><span style="font-weight: bold;">Run Frequency</span>: <span style="font-family:Courier New;">&lt;Select from the dropdown list, for example, Run Once on Activation&gt;</span></p><p><span style="font-weight: bold;">Checking Period</span>: <span style="font-family:Courier New;">&lt;Select as appropriate, for example, Data range of last year&gt;</span></p><span aria-labelledby="n1t" style="color: #346187; "><div><strong>Note</strong></div><p>A <span style="font-weight: bold;">Checking Period</span> is a time period by which the data checked by automated procedures are filtered. You need to define the checking period used for each run of a work package when the <span style="font-weight: bold;">Reference Period is Calendar Date or Fiscal Period</span>.</p></span><p>Navigate to the <span style="font-weight: bold;">Controls and Procedures</span> tab.</p><p>Choose <span style="font-weight: bold;">Add</span>. Select the Control created in the previous steps and choose <span style="font-weight: bold;">OK</span>.</p><p>Select the Destinations in the <span style="font-weight: bold;">Enabled Destinations</span> column to enable the Destinations for the Work Package.</p><p>Choose the <span style="font-weight: bold;">Description</span> tab, and enter as appropriate.</p><p>Choose <span style="font-weight: bold;">Create</span>.</p> | <p>New Work Package is created.</p>
[14 empty] | Create Work Package |  |  |  | Activate the Work Package | <p>Choose <span style="font-weight: bold;">Activate</span>.</p> | <p>The work package is active and work package run will be triggered as planned.</p>
[14 empty] | Display Automated Procedure Run Result |  |  |  | Information | <h2>Purpose</h2><p>The work package created above will run as schedule after activation. The compliance specialist or the compliance manager log on to the SAP Risk and Assurance Management system to view the result of automated procedure run and take actions for the risk.</p><h2>Prerequisite</h2><p>Before you start the test procedures, make sure the work package is scheduled successfully and the first run is finished.</p><h2>Procedure</h2>
[14 empty] | Display Automated Procedure Run Result |  |  |  | Log On | <p>Log on to SAP Risk and Assurance Management as Manager.</p>
[14 empty] | Display Automated Procedure Run Result |  |  |  | Display the Procedure Runs Results | <p>Open <span style="font-weight: bold;">Display Automated Procedure Runs</span>.</p><p>In the <span style="font-weight: bold;">Procedure Runs</span> list, select the completed Procedure Runs scheduled by the work package which was created in the previous steps.</p> | <p>The detailed run results report will be displayed.</p>
[14 empty] | Display Automated Procedure Run Result |  |  |  | Remediate the Risks (Optional) | <p>Please refer to Use Cases for more details.</p>